## Sheet1
| Area | What Went Wrong | Proposed Solution | Status | Assignee | Comments
1 | Communication | Lack of instant messaging communication channel in the start of the implementation. | Ideally we should setup a IM group where team can quickly exchange thoughts and queries. | Open
2 | Planning | Inadequate requests by Partner : Parloa was sharing information in bits & pieces | Ideally they should come up with the low level detailed plan i.e. a kind of a checklist, that could be used in one go to get the requirements from the stakeholders particularly client. | Open
3 | Communication | No back ground shared Prior to the calls | Ideally host should share some background/agenda in the meeting invite and specifically | Open
4 | Communication | Inadequate Escalation path: | resources involved in the task must be able to address in person rather than escalation to each others supervisor's | Open
5 | Stakeholder Engagement | some teams were not involved from the start. | we should involve the teams from the start. involve affected team in the advance stages | Open
6 | Resource Management | Lack of SME (telephony) | Ideally we must have a dedicated Telephony resource who can quickly work on the solutons. At the same time we can upskill exisitng resources. | Open
7 | Communication | Lack of documentation - host often doesn’t document the extraction of the meeting and associated action items. Which causes issues to track the open items | Ideally host should document the meeting notes and clearly specify the action items and owner assigned to it. It helps in tracking the progress and recall what had discussed across meetings. | Open
8 |  | PM works vertically as well as horizontally | Dedicated SME's should be hired to be a part of the team who focuses on the certain vertical and PM's should be responsible managing the horizontally. | Open
9 | Leadership | Lack of Governance |  | Open
10 | Time Management | unrealistic deadlines for implementations | Adjust the project timeline to focus on delivering critical features first, ensuring quality and long-term success while mitigating risks associated with unrealistic deadlines | Open
11 | Resource Management | overallocation of the resources on Wave iX impact on other verticals of projects | Optimize resource allocation for Wave iX to prevent disruptions in other vertical projects, ensuring balanced workloads and sustained productivity across all teams | Open
12 | Communication | Insufficient Training: Users struggled due to Inadequate hands | Timely Training sessions needs to be scheduled with right audience, vast audience , with required manuals. | Open
13 | Communication | Inadequate way of setting up expectations | Ideally we need to clearly setup expectation in terms of their role. | Open
14 | Communication | Inadequate meeting subjects: sometimes multiple mail threads were created that address the same piece | ideally we should chain the conversations under a certain thread to easily find out the streams. | Open
15 | Process Management | inadequate Process Adherence: Most of the activities were executed haphazardly | despite of having a critical nature of work and tight deadlines, we can still devise a process and adhere to it. | Open
16 | Communication | Inadequate Transparency: |  | Open
17 | Time Management | Date was committed without discussed with the implementation team. | Ideally once scope is defined, the scope needs to be presented with the team and identify the activities, resources, time durations and dependencies. Based on that the timelines needs to be built and share across board. | Open
18 | Communication | Delays in client response | This may vary client to client. Ideally what we can do is to plan the client activity keeping certain contingency reserves. also we can collect the list of item on which we require client feedback. | Open
What went well
1 | leaning & Domain | Gained expertise in leveraging AI (LLM) tools effectively.
2 | leaning & Domain | Acquired in-depth technical knowledge of telephony systems.
3 | leaning & Domain | Developed hands-on proficiency with the Genesys telephony platform.
4 | Resource Management | Demonstrated strong and collaborative teamwork throughout the project.
5 | Scope Management | Scoped the project phases effectively, ensuring clarity and feasibility.
6 | leaning & Domain | Successfully configured SIP and PSTN trunks for efficient call routing.
7 | Resource Management | Established redundant resources to support implementation efforts and ensure continuity.
8 | Process Management | Developed comprehensive implementation plans for Wave iX Chatbot, Wave iX Translate, and Wave iX Virtual Agent.
9 | Procurement | Received timely and effective vendor support for troubleshooting issues.
10 | Communication | Benefited from well-documented and detailed API references.
11 | Communication | Maintained consistent weekly touchpoints with the client, partners, and internal project teams.
12 | Execution | Achieved successful implementation milestones as planned.
13 | leaning & Domain | Gained practical experience with partner tools, enhancing implementation capabilities.
14 | Communication | Delivered consistent weekly progress reports on the implementation status.
15 | Resource Management | Established a high-level RACI (Responsible, Accountable, Consulted, and Informed) matrix for clarity in roles.
16 | Communication | Created an effective and organized email distribution list for seamless communication.
17 | Communication | Adequate Knowledge base: maintain recordings, partner manuals, checklist on the centralized repository