## Sheet1
Sr. | Projects | Activity Sequence | Status
1 | Envoy Enterprise Deployment | License & Hardware Procurement and delivery in US | Completed
|  | Movement to Destination Sites in Progress | In-Progress
|  | Feature set demo and review with Global Compliance Leadership | Completed
|  | Design & Configuration. | In-Progress
|  | Final Flow and workability review | Pending
|  | Deployment | Pending
2 | Wave iX - Krisp AL PH Conifer Pilot | Formal 30 days Pilot | In-Progress
|  | First Weekly feedback review | Pending
|  | 30 days data analysis review | Pending
|  | Final Decision from business side | Pending
3 | Wave iX - Krisp AL PK SD Pilot | Vendor discussion | Completed
|  | Resource Alignment | Completed
|  | SD Testers alignment | Completed
|  | Test license allocation | Completed
|  | App deployment and configuration | In-Progress
|  | 30 days pilot | Pending
|  | First Weekly feedback review | Pending
|  | 30 days data analysis review | Pending
|  | Final Decision from business side | Pending
4 | Wave iX - Automate - FlipCX listen mode - Leslies | Project Iniciation (to be made live by 17th Nov) | Completed
|  | ibex and vendor resource allocation | Completed
|  | Vendor side portal setup | Completed
|  | Ibex Genesys side configuration (ticket already sumbitedto CGC) | Pending
|  | CGC / Vendor Joint config call | Pending
|  | 15 days Listen mode start | Pending
|  | Disable listen Mode | Pending
|  | Data Analysis and Decision | Pending
5 | AWS Resource Optimization Phase-4 Linux | Decision to move machines from AES to On-Prem | Completed
|  | Paralell On-Prem Machines Provision | Completed
|  | AWS to On Prem Migration | In-Progress
|  | AWS Decom | Pending
6 | AWS Resource Optimization Phase-6 - S3 Bucket | Capacity and providon review | Completed
|  | Data Validations and purging | Completed
|  | Retension policy review | In-Progress
|  | bucket resizing and policy update | Pending
7 | Wave iX - Parloa RTT & AMP | Project Intake
Discovery Document
Meeting with Prgram CS, Ops, QA, Training
Meeting with Vendor to discuss Discovery Document

## krisp
Sr. # | Task | Description | Owner
1 | Meeting with vendor | initial demo and introduction call with vendor to review the technology and realtime working | PMO | 4 days
2 | Target Ops identification | identify test campaign/agents on which pilot needs to be performed. | PMO + Leadership | 4-5 BD
3 | Client Approval | gather respective client approval to implement with production calls for maximum data analaysis | CS | 2-4 weeks
4 | Krisp Team Creation | have vendor create a saparate krisp team on portal for better tracking of licenses | Vendor | 1-2 BD
5 | Kickoff Call | kickoff call with relevant CS, ops, IT, testers to explain the product and process for the pilot | PMO | 1-2 BD
6 | Krisp Deployment | provide exe file and secret key to local IT FS for deployment on test PCs | IT FS | 3-5 BD
7 | Testing and Start Pilot | schedule a testing call first to completely test the product and train agents as well. Then start the 30 days pilot with production calls | PMO + IT FS | 30 BD
8 | QA Feedback Form | provide feedback form to QA to review random calls daily for test agents | PMO
9 | Daily Feedback Reports | QA to share daily call recording feedback. | QA + Ops
10 | Weekly Review Call | setup weekly data and recording analysis call with ops, tester and vendor to discuss shortcomings and performance. | PMO
11 | Final Review Call | final call with CS, PMO, wave-ix, Ops to get final review of 30 days performance | PMO
12 | Go - No Go | call with leadership to discuss product performance | PMO
Cost Assessment
Cost Decision
Involve Procurement

## Detailed Krisp plan
Meeting with Vendor | Details | Responsible Team | Start Date | End Date | Duration | Status
Vendor Introduction | Schedule a meeting with the vendor to discuss the product, its capabilities, and the pilot approach. | PMO | 2024-11-18 | 2024-11-19 | 2
Product Demo | Review the product’s features through a live demo to understand its technology and real-time application. | Vendor | 2024-11-20 | 2024-11-20 | 1
Query Resolution | Address any questions or concerns from the stakeholders about the product or implementation. | PMO + Vendor | 2024-11-21 | 2024-11-21 | 1
Next Steps Planning | Agree on the timeline, responsibilities, and milestones for the pilot program. | PMO + Vendor | 2024-11-22 | 2024-11-22 | 1
Target Operations Identification
Campaign Selection | Identify specific campaigns that are suitable for the pilot based on workload and customer impact. | PMO + Leadership | 2024-11-23 | 2024-11-25 | 3
Agent Selection | Shortlist agents based on criteria such as performance, availability, and tech-savviness. | Operations | 2024-11-26 | 2024-11-26 | 1
Role Assignment | Define roles for selected agents, such as test agents and reviewers, to streamline pilot activities. | Operations | 2024-11-27 | 2024-11-27 | 1
Client Approval
Client Presentation | Present the pilot’s objectives, scope, and expected benefits to the client for alignment. | Client Services (CS) | 2024-11-28 | 2024-11-28 | 1
Approval Process | Address client concerns, adjust scope if needed, and formally document their approval. | Client + PMO | 2024-11-29 | 2024-12-01 | 3
Data Sharing Agreement | Ensure a clear understanding of data sharing, security, and compliance between all parties. | CS | 2024-12-02 | 2024-12-02 | 1
Krisp Team Creation
Dedicated Team Setup | Coordinate with the vendor to set up a dedicated Krisp team for license management. | Vendor | 2024-12-03 | 2024-12-03 | 1
Portal Configuration | Ensure that the team portal is configured for license tracking and agent monitoring. | Vendor | 2024-12-04 | 2024-12-04 | 1
Access Provisioning | Provide access credentials for PMO and IT to monitor the Krisp platform. | Vendor | 2024-12-05 | 2024-12-05 | 1
Kickoff Call
Stakeholder Meeting | Schedule a kickoff call with CS, IT, Operations, testers, and the vendor. | PMO | 2024-12-06 | 2024-12-06 | 1
Process Explanation | Outline the pilot's process, milestones, and agent responsibilities. | PMO | 2024-12-07 | 2024-12-07 | 1
Q&A Session | Address any questions from stakeholders to ensure alignment. | PMO + Vendor | 2024-12-08 | 2024-12-08 | 1
Krisp Deployment
File Provisioning | Share the Krisp executable file and secret key with the IT support team. | Vendor | 2024-12-09 | 2024-12-09 | 1
Software Installation | Deploy the software on test PCs for selected agents. | IT FS | 2024-12-10 | 2024-12-12 | 3
System Validation | Ensure that the software is functioning properly and integrated with existing tools. | IT FS | 2024-12-13 | 2024-12-13 | 1
Testing and Start Pilot
Agent Training | Train test agents on using the Krisp platform effectively. | Operations + Vendor | 2024-12-14 | 2024-12-14 | 1
Testing Phase | Conduct a trial run to verify Krisp’s functionality and address any issues. | PMO + IT FS | 2024-12-15 | 2024-12-15 | 1
Pilot Kickoff | Launch the 30-day pilot with production calls once testing is complete. | PMO + IT FS | 2024-12-16 | 2025-01-14 | 30
QA Feedback Form
Form Design | Create a structured feedback form to capture key observations about call quality. | QA | 2025-01-15 | 2025-01-15 | 1
Distribution | Share the feedback form with QA and test agents for daily inputs. | PMO + QA | 2025-01-16 | 2025-01-16 | 1
Data Consolidation | Collect and review daily feedback for patterns or issues. | QA | 2025-01-17 | 2025-01-17 | 1
Daily Feedback Reports
Feedback Collection | Collect daily call recording feedback from QA and Operations teams. | QA + Operations | 2025-01-18 | 2025-01-18 | 1
Issue Logging | Identify and log any recurring issues or challenges during the pilot. | QA | 2025-01-19 | 2025-01-19 | 1
Feedback Sharing | Share findings with PMO and stakeholders to make data-driven adjustments. | QA | 2025-01-20 | 2025-01-20 | 1
Weekly Review Call
Progress Review | Discuss pilot progress, review weekly data, and identify any gaps or improvement areas. | PMO | 2025-01-21 | 2025-01-21 | 1
Performance Analysis | Analyze key metrics such as call quality and agent productivity. | QA + Vendor | 2025-01-22 | 2025-01-24 | 3
Issue Resolution | Address outstanding issues or refine the pilot process based on feedback. | PMO + Operations | 2025-01-25 | 2025-02-18 | 25
Final Review Call - Go-No Go |  |  |  |  | 3
Performance Evaluation | Present the overall results of the 30-day pilot, including agent performance and QA feedback. | PMO + QA | 2025-02-19 | 2025-03-15 | 25
Stakeholder Discussion | Discuss findings and potential adjustments with stakeholders (CS, PMO, and Vendor). | PMO + CS | 2025-03-16 | 2025-03-15
Decision Preparation | Prepare for the Go-No Go decision based on pilot outcomes. | PMO | 2025-03-16 | 2025-03-18 | 3
124
Formulas:
End Date = [Start Date]+[Duration]-1
Start Date = [End Date, row above]+1