## Sheet1
step | Phase | Description | Responsibility | Start Date | End Date | Duration | Status | Comments
Discovery
| Meeting with Client | sharing agenda with the client, ptich, demostration | S. Pavel/E. Guerra
| Client Approval | client's buying | S. Pavel/E. Guerra
| Intent collection/Usecase identification | Confirm business requirements, use cases, and supported channels. Intent collections | IT PMO, Business Teams
| Collect Ips and URL from Parloa and Genesys | need to collect Ips, FQDN that needs to be whitelisted on parloa and genesys end | PMO |  |  |  | Not Started | Schedule stakeholder meetings.
| Creation of DID and Pvt Numbers, orgs |  | CGC
Planning
3 | Resource Allocation | Assign roles for Parloas, network engineers, and admins. | IT PMO |  |  | 2 | Not Started | Confirm availability of resources.
4 | API Whitelisting | Whitelist IPs and endpoints for Parloa’s APIs. | GNOC |  |  | 2 | Not Started | Verify Parloa’s IP details with vendor.
Trunk Setup
5 | Trunk Setup between Parloa and Ibex Genesys | Configure SIP trunks for voice traffic, ensuring codec compatibility. | CGC |  |  | 3 | Not Started | Confirm SIP protocol versions used.
6 | API Integration | Implement Parloa’s API in Genesys workflows for call/chat translation. | Parloa, Admin |  |  | 5 | Not Started | Use Genesys Architect for workflow design.
7 | Call Routing | Define and test call-routing rules for integration. | CGC |  |  | 3 | Not Started | Validate translation routing for accuracy.
8 | Data Handling | Ensure data compliance, including encryption and masking sensitive info. |  |  |  | 3 | Not Started | Align with GDPR/CCPA if applicable.
9 | Testing (Voice & Chat) | Test call/chat flows, translation, and system stability under load. |  |  |  | 4 | Not Started | Include fallback scenarios in test cases.
10 | UAT | Validate translation quality and performance with business users. |  |  |  | 5 | Not Started | Adjust schedule for holidays if needed.
11 | Training | Train agents/admins and create troubleshooting guides. | IT PMO, Vendor |  |  | 3 | Not Started | Schedule multiple training sessions if needed.
12 | Deployment | Roll out integration regionally and monitor performance logs. | CGC, IT PMO |  |  | 5 | Not Started | Define rollback plan in case of issues.
13 | Post-Deployment Review | Collect feedback, analyze performance, and refine configuration. | IT PMO |  |  | 3 | Not Started | Host a retrospective session with stakeholders.

## Configure Parloa-Genesys
Phase | Task | Description | Assignee | Start Date | End Date | Duration (Days) | Status | Risks
Discovery | Meeting with Client | sharing agenda with the client, ptich, demostration | S. Pavel/E. Guerra |  |  |  | Not Started
| Content Discovery | Insight on Call Data, Focus use cases and goal statement for RTT | IT PMO/S. Pavel/E. Guerra/Client POC |  |  |  | Not Started
| Understanding Client's ACD | Discuss and review Cross platform dependencies, Languages required, Amazon Connect, Five9, Avaya etc | IT PMO/S. Pavel/E. Guerra/Client POC |  |  |  | Not Started
Planning | Define project scope and objectives | Collect requirements, Transform requirements into Scope, create WBS, | IT PMO |  |  |  | Not Started | Scope creep if requirements are unclear
| Resource Identification & Allocation from Client & Wave iX Translate Teams, Ops & Testers | allocate project resources across different teams i.e.Wave iX Translate genesys etc | IT PMO |  |  |  | Not Started | Missing key stakeholders
| identify use cases - Call flows | How operations will use and test the feature. | IT PMO |  |  |  | Not Started
| Identify activities and Establish Project Schedule | identify activities, build Activity Network Diagram, Identify Critical pathm identify Durations, Manage Reserves, build Project Schedule. | IT PMO |  |  |  | Not Started
| Publish Ptoject Timelines and Get Sign Off | Publish Ptoject Timelines and Get Sign Off | IT PMO |  |  |  | Not Started | Miscommunication between teams
Tech Discovery | Tech Sessions with Client | Tech workshop with client’s telephony experts.Telephony experts to advise on system integration incl caller validation | Client POC & Wave iX Translate |  |  |  | Not Started
| Client Platform Access Provision | Client Platform Access Provision | IT PMO |  |  |  | Not Started
| Telephony system compatibility | Wave iX will check if SIPs configured and enabled in client's telepohony system. | Wave iX Translate |  |  |  | Not Started
| CCaas Compatibility | Wave iX will check if Client's platform is compatible with Wave iX Translate | Wave iX Translate |  |  |  | Not Started
| API and Telephony Platform Dependencies | Voice Media Codec Support, Audio Quality, API documentation and accessibility | Wave iX Translate |  |  |  | Not Started
| Languages required | Language Support: Verify if the telephony platform and Wave iX Translate support the same languages for voice and text interactions. language model should match the target audience's language. | Wave iX Translate |  |  |  | Not Started
| Customize configuration for client | General configuration of prompts for GPT model, internal testing | Wave iX Translate |  |  |  | Not Started
| Confirmation to the Client | Based on the above discovery activity | S. Pavel/E. Guerra |  |  |  | Not Started
Design | Collect IPs and URL from Wave iX Translate | need to collect IPs, FQDN that needs to be whitelisted on client ACD | IT PMO |  |  |  | Not Started
| Collect IPs and URL from Client ACD platform | need to collect IPs, FQDN that needs to be whitelisted on Wave iX Translate | IT PMO |  |  |  | Not Started
| Validate network requirements | Open the required ports and whitelist IP ranges as specified in both Genesys and Wave iX Translate documentation. | IT PMO |  |  |  | Not Started
| Request For ticket to Whitelist the traffic between two end | Request For ticket to Whitelist the traffic between two ends | IT PMO |  |  |  | Not Started
| Confirm all the information required to configure Translate Engine | In this task, we will gather all the information required to configure translate platform | Client POC/Wave iX Translate |  |  |  | Not Started
Implementation | Creation of DID and Pvt Numbers, orgs | Creation of DID and Pvt Numbers, orgs | Client POC/Wave iX Translate |  |  |  | Not Started
| Set up SIP/PSTN trunk between Wave iX Translate and Client ACD | Set up SIP/PSTN trunk between Wave iX Translate and Client ACD | Client POC/Wave iX Translate |  |  |  | Not Started | Incorrect SIP trunk settings
| Configure SIP trunk in Wave iX Translate | Configure SIP trunk in Wave iX Translate | Wave iX Translate |  |  |  | Not Started | Configuration delays
| Whitelist IPs and APIs, FQDN, URLs for Client ACD | Whitelist IPs and APIs, FQDN, URLs for Client ACD | Wave iX Translate |  |  |  | Not Started
| Whitelist IPs and APIs, FQDN, URLs for Wave iX | Whitelist IPs and APIs, FQDN, URLs for Wave iX | Client POC |  |  |  | Not Started
| Configure Ibex Translate for each requested language | In this phase, Wave iX team will configure translate platform | Wave iX Translate |  |  |  | Not Started
| Wave iX LLM configuration and Optimisation | In this phase, Wave iX team will Optimise the out of the box features | Wave iX Translate |  |  |  | Not Started | Firewall rules blocking communication
Training & Testing | Access provisionings for Ops | need to provide access to the Operations | Wave iX Translate |  |  |  | Not Started
| Train the Trainer | Need to train the trainer | Wave iX Translate |  |  |  | Not Started
| Train the Agents | Train the Agents | Operations Team |  |  |  | Not Started
| Perform test calls from Genesys to Wave iX Translate | 1. test calls. 2. Conduct language-specific testing to evaluate dialog flows, pronunciation accuracy, and customer satisfaction 3. TTS-STT testing | Operations Team |  |  |  | Not Started | Signaling or audio quality issues
| Test call flows and workflows | Test call flows and workflows | Operations Team |  |  |  | Not Started | Workflow misalignment between platforms
| Signoff for Go-Live | Signoff for Go-Live | Operations Team |  |  |  | Not Started | Resolution delays impacting timelines
Deployment | Formal Ticket & Notification, Bridge reservations | Finalize deployment plan, notify client, Ops and teams | IT PMO |  |  |  | Not Started
| Execute deployment | Deployment | Client POC & Wave iX Translate |  |  |  | Not Started | Deployment errors or unexpected downtime
| Post-deployment monitoring activity | Monitoring of calls and project KPIs, gather agent, feedback for improvements | Client POC |  |  |  | Not Started | Latency or connectivity issues post-deployment
Closure | Document lessons learned | Document lessons learned | IT PMO |  |  |  | Not Started | Missing critical feedback
| Handover to operations | Handover to operations | Operations Team |  |  |  | Not Started | Incomplete documentation or training