## Sheet1
estone | Task | Description | Assignee | Start Date | Duration | Status | Comment
1 | Project Initiation | Formally initiate the project by defining objectives, scope, and stakeholders. | IT PMO | 2025-01-02 | 1 week | Planned
2 | Requirements Gathering | Collect detailed functional and technical requirements for Parloa AMP integration. | IT PMO, Operations | 2025-08-02 | 2 weeks | Planned
3 | Solution Design | Develop the integration architecture and design specifications for Parloa AMP. | Parloa Team, IT PMO | 22/02/2025 | 2 weeks | Planned
4 | Infrastructure Preparation | Set up necessary infrastructure, including telephony systems and network configurations. | IT PMO | 2025-07-03 | 3 weeks | Planned
5 | Parloa AMP Installation | Install and configure the Parloa AMP platform within the prepared infrastructure. | Parloa Team | 28/03/2025 | 1 week | Planned
6 | Integration with CCaaS | Integrate Parloa AMP with existing Contact Center as a Service (CCaaS) platforms. | Parloa Team, IT PMO | 2025-04-04 | 2 weeks | Planned
7 | AI Agent Configuration | Configure AI agents to handle specific customer service tasks and workflows. | Parloa Team, Operations | 18/04/2025 | 2 weeks | Planned
8 | Testing and Quality Assurance | Conduct comprehensive testing to ensure system functionality, performance, and reliability. | IT PMO, Operations | 2025-02-05 | 3 weeks | Planned
9 | User Training | Train end-users and administrators on the features and operation of Parloa AMP. | Parloa Team, Operations | 23/05/2025 | 1 week | Planned
10 | Go-Live Preparation | Prepare for system launch, including final checks and user readiness assessments. | IT PMO, Operations | 30/05/2025 | 1 week | Planned
11 | System Go-Live | Officially launch Parloa AMP into the production environment for operational use. | IT PMO, Operations | 2025-06-06 | 1 day | Planned
12 | Post-Implementation Review | Evaluate the implementation process and system performance; document lessons learned. | IT PMO, Operations | 2025-07-06 | 1 week | Planned

## Sheet2
Milestone | Task | Description | Assignee | Start Date | Duration | Status | Comment
1. Project Initiation | Kickoff Meeting | Align stakeholders on objectives, deliverables, timelines, and roles. | IT PMO, Parloa Team, Operations, waveIX | 2025-01-02 | 1 day | Planned
| Stakeholder Identification | Identify and confirm all stakeholders involved in the project. | IT PMO | 2025-02-02 | 1 day | Planned
| Documentation Setup | Establish a shared workspace for all project documentation and communication. | IT PMO | 2025-03-02 | 2 days | Planned
2. Requirements Gathering | Requirement Interviews | Conduct interviews with operations and tech teams to gather functional needs. | IT PMO, Operations | 2025-08-02 | 3 days | Planned
| Process Mapping | Document existing workflows and identify areas for automation using Parloa AMP. | Operations, IT PMO | 2025-12-02 | 4 days | Planned
| AI Use Case Identification | Define specific agent-related tasks for automation (e.g., call routing, agent alerts). | Parloa Team, Operations | 16/02/2025 | 1 week | Planned
3. Solution Design | Architecture Blueprint Creation | Develop a high-level integration design, including CCaaS, telephony, and Parloa AMP. | Parloa Team | 22/02/2025 | 5 days | Planned
| Security and Compliance Review | Ensure solution design meets data privacy, security, and compliance standards. | IT PMO, waveIX | 28/02/2025 | 3 days | Planned
| Approval from Stakeholders | Review and sign off on the design document. | All Teams | 2025-04-03 | 2 days | Planned
4. Infrastructure Preparation | Environment Assessment | Audit existing IT infrastructure, including telephony and network systems. | IT PMO, waveIX | 2025-07-03 | 3 days | Planned
| Network Configuration | Set up network changes required for Parloa AMP integration. | waveIX | 2025-11-03 | 1 week | Planned
| Telephony Configuration | Configure telephony systems to enable Parloa AMP connections. | waveIX, Parloa Team | 18/03/2025 | 1 week | Planned
5. Parloa AMP Installation | Platform Installation | Install Parloa AMP in the designated environment. | Parloa Team | 28/03/2025 | 3 days | Planned
| Connectivity Testing | Test telephony connectivity between Parloa AMP and CCaaS systems. | Parloa Team, IT PMO | 2025-01-04 | 2 days | Planned
6. Integration with CCaaS | API Integration Development | Develop APIs to link Parloa AMP with CCaaS for data exchange and task automation. | Parloa Team | 2025-04-04 | 1 week | Planned
| Integration Testing | Validate successful API integration through functional and load testing. | IT PMO, Parloa Team | 2025-11-04 | 5 days | Planned
7. AI Agent Configuration | Task Mapping to AI | Map specific agent workflows and tasks (e.g., escalations, call summaries) to AI capabilities. | Parloa Team, Operations | 18/04/2025 | 3 days | Planned
| AI Model Training | Train AI models to perform assigned tasks effectively. | Parloa Team | 22/04/2025 | 1 week | Planned
| Workflow Testing | Test AI-driven workflows in a simulated environment to ensure accuracy and reliability. | Operations, Parloa Team | 29/04/2025 | 3 days | Planned
8. Testing and Quality Assurance | UAT (User Acceptance Testing) | Involve users to validate that the system meets operational requirements. | Operations | 2025-02-05 | 2 weeks | Planned
| Bug Fixes and Optimization | Address issues identified during testing and optimize system performance. | IT PMO, Parloa Team | 16/05/2025 | 1 week | Planned
9. User Training | Training Material Preparation | Develop training guides and videos for end users and administrators. | Parloa Team | 23/05/2025 | 3 days | Planned
| Conduct Training Sessions | Deliver training sessions to users and admin staff. | Parloa Team | 27/05/2025 | 2 days | Planned
10. Go-Live Preparation | Final Configuration Check | Perform a final system audit to ensure all configurations are correct. | IT PMO, waveIX | 30/05/2025 | 2 days | Planned
| Go-Live Plan Validation | Validate readiness for system launch, including fallback procedures. | IT PMO, Operations | 2025-02-06 | 2 days | Planned
11. System Go-Live | Deployment | Launch Parloa AMP into the production environment. | IT PMO | 2025-06-06 | 1 day | Planned
12. Post-Implementation Review | Performance Monitoring | Monitor system performance and identify areas for improvement. | IT PMO, Operations | 2025-07-06 | 5 days | Planned
| Lessons Learned Documentation | Document successes, challenges, and lessons for future projects. | IT PMO | 14/06/2025 | 2 days | Planned

## final
Task(s) & Milestones | Desctiption | Assignee | Start Date | End Date | Duration | Status | Comment
1. Intro Call (1 Week)
a. Intro call with WaveIX team | i.e. all participants partner, PMO, Pavel & Eric. | WaveIX Team
b. intro call with client | i.e. what value we are delivering with the proposed solution. | WaveIX Team,Client
2. Discovery Workshop (1 Week)
a. Identify Stakeholders | i.e. Roles and Responsibilities from Client and WaveIX end. | WaveIX Team
b. Gather Operational Requirements | i.e. Document client’s operational workflows and gather other supporting materials and documentation from Client services or Operations | WaveIX Team, CS, Ops
c. Identify Key Operational Pain Points | i.e. Highlight areas for improvement | WaveIX Team, CS, Ops
d. Identify and Establish KPI(s) and their current and forecasted value. | Meet up with the CS and Operations and gather list of KPIs measuring the success criteria | WaveIX Team, CS, Ops
e. Complaine Review . | Ensure solution design meets data privacy, security, and compliance standards. | WaveIX Team, Security
3. Tech Discovery (1 Week)
a. Tech sessions for understanding client platform | e.g. CCaas? CRM? KB? | WaveIX Team/Client
b. Assessment of the platform and see if we need to develop customizations for the enablement. | WaveIX team will check if we have out of the box integration solution or do we need to develop customize code | WaveIX Team
c. Collect URLs VoIP/Https from both end to whitelist | for establishing the Secure communication whitelisting from both ends needs to be done | WaveIX Team
d. Request Whitelisting of the WaveIX AI Agent URLS on Client CCaaS and CRM. |  | WaveIX Team
e. System Architectural Diagram | i.e. diagram to visually analyze the configuration scenario | WaveIX Team/Ops
f. Review API Documentation and prepare questions |  | WaveIX Team
g. Get API Access from source CCaaS, CRM, KB i.e. User Creation | Access provision from the on the CCaaS, CRM, KBs. | Client
h. Tech session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client. | Conduct a session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client and discuss the API details | WaveIX Team/Client
4. Listen Mode Enablement(3weeks)
a. Assess Telephony Requirements | i.e. DID creation, Call Forwarding | WaveIX Team
b. Plan Telephony Integration | i.e. raise formal tickets or request | WaveIX Team
c. Implement Telephony Integration | Implement Telephony Integration | WaveIX Team
d. Integration Testing | i.e. make Test Calls E2E and monitor logs, take Go-No Go | WaveIX Team
e. Enablement of Listening Mode | Enablement of Listening Mode | WaveIX Team
f. Listen Mode Data Analytics with Client | Listen Mode Data Analytics with Client | WaveIX Team
i. Collect Data and build Analytics |  | BI
ii. Use case identification, |  | BI
iii. Draw Flows, understanding Flows |  | BI
5. Scoping(1 Week)
a. Tech sessions with Client POC on Analytics on Listen Mode. | showcase them possession of the calls traffic | WaveIX Team/Client
b. Use Case identification that needs to be automated. | Propose set of usecase to client that can be automated and get beneficial. | WaveIX Team/Client
c. Scoping Call with Client i.e. What needs to be delivered in Subsequent Phases | i.e. Phase 1 Flow 1, Flow2, Flow 3 .Phase 2 Flow 4, Flow 5, Flow 6. | WaveIX Team/Client
d. Initiate Tech Session with Client on Mapping Usecases with APIs | Initiate Tech Session with Client on Mapping Usecases with APIs | WaveIX Team/Client
e. Identify Use cases and API Endpoints i.e. tech sessions between the Clients and WaveIX team | Identify Use cases and API Endpoints i.e. tech sessions between the Clients and WaveIX team | WaveIX Team/Client
f. Develop Formal Scoping Document and Signoff | Formal Scoping Document and Signoff | WaveIX Team/Client
6. Integration in Telephony i.e. SIP or PSTN (2 Weeks)
a. Assess Telephony Requirements |  | WaveIX Team
b. Plan Telephony Integration |  | WaveIX Team
c. Implement Telephony Integration |  | WaveIX Team
g. AI Agent(bot) Development - by CXD(parloa) | using Parloa Studio, build a BOT AI agent and assign Task | WaveIX Team
h. CX Design: Integrate knowledge sources |  | WaveIX Team
I. CX Design: Set up simulations and evaluations |  | WaveIX Team
j. CX Design: AMP Prompt Engineering |  | WaveIX Team
7. Integration Backend System (2 Weeks) | i.e. Parloa services Integration with CCaaS's and CRM's APIs.
c. Implementation of Use Cases in Parloa and Integration Feedback | Implementation of Use Cases in Parloa and Integration Feedback | WaveIX Team
d. Product Increment Review & Retro | demo | WaveIX Team
e. Go-No Go. | Go No Go | WaveIX Team
8. User Acceptance Testing & Optimization
a. Identification of Test Case with the help of CS & Ops. | Ops will come up with the pre-defined test cases | Ops
b. Schedule and Conduct Session for testing on Official Bridges. | Schedule and Conduct Session for testing on Official Bridges. | WaveIX Team
c. Review Results with WaveIX Team | Review Results with WaveIX Team and see if we need to develop | WaveIX Team
d. Adaptation | retrospective | WaveIX Team
9. Go-Live
a. Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | WaveIX Team
b. Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | WaveIX Team
c. Bridge Reservation and Go-Live | Bridge Reservation and Go-Live | WaveIX Team
d. Monitoring bridge | Monitoring bridge | WaveIX Team
10. Ongoing Testing and Review of Conversations in AMP
a. Refinements | Refinements | WaveIX Team
b. Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Build Performance Report for the implementation and Monitor of KPI i.e. NPS | WaveIX Team