## Slide 1
Life Cycle
& 3rd Party Tools

## Slide 2
Authenticate & Automate
AI-driven voice and IVR automation platform that streamlines customer service by automating routine tasks, enhancing efficiency, and improving customer experiences.
Wave iX AI Agent
Active Opportunities:
Custom Ink
Leslie
Redroof Inc.
TiVo
Mint Mobile
Pipeline Opportunities :
Transcard
Wave iX Translate
Active Opportunities:
Red Roof Inn
Pipeline Opportunities :
Modivcare,
Saferide
UPS
Transcard
Lyft
Square Trade
Mercedes Benz

## Slide 3
Mint Mobile – Wave iX Agent AI
PROGRESS UPDATE
12/19:Call flows and routing destinations have been shared with client and approved with little changes.
12/20: Agent’s personae have been shared with the client.
12/20:Pavel has shared concise FAQs with Wave iX team.
12/24: configuration changes figured out and shared with client. Client will approve after holidays.
We have setup a session to extract low level diagram of the required flows in the Genesys.
Sample calls are requested to Operations.
Test plan developed and shared with QA – tech teams.
NEXT STEPS
Wave iX team share the sample recordings for conversation learning
Client endorsement on configurational changes on the Mint Genesys is awaited
Wave iX team to share the low-level design diagrams for the bot implementation.
AI BOT Design Sessions
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Delayed Implementation | Bad impact on client in terms of implementation expertise | Parloa engaged on top priority to devise solution. | TBD | Wave iX | In-Progress
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | In Progress
Testing & Pre Go-:Live | TBD | Operations | In Progress
Go-:Live | TBD | Operations | To-do

## Slide 4
RedRoof Inn – Wave iX Translate
PROGRESS UPDATE
Wave iX is still devising a solution to segregate “Guest Relations” and “Booking” calls.
Once solution will be devised, wave iX will develop configurations that will contain some changes to the platform.
client approval will be required on the proposed changes.
We also need to review the documentation for establishing the connectivity between our wave IX Translate solution and Amazon connect.
Need to see if wave ix can help otherwise, we need to ask client to engage their AWS professional services for the connectivity
Wave iX has shared tentative plan for the implementation
NEXT STEPS
Wave iX to share the DID for the “Guest relations” for segregating the routes.
Tech session on connectivity between Amazon connect and Wave iX translate.
Training
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Discovery | 11/15 | Wave iX | Completed
Planning | 12/6 | Wave iX | Completed
Tech Discovery | 12/19 | Wave iX | In-Progress
Design | TBD | Wave iX | To-do
Implementation | TBD | Wave iX | To-do
Training & Testing | TBD | Ops/CS | To-do
Deplooyment | TBD | Wave iX | To-do

## Slide 5
RedRoof Inn – Wave iX AI Agent
PROGRESS UPDATE
Retro Listen mode was requested to Wave iX AI agent for listening 500 calls on the box space.
Ibex has provisioned 500calls to Wave iX AI agent
Post listen mode data presented to CS.
CS opted for automating “Guest Relation” use case for the MVP. As it has less Credit card need.
We will cover CC based use case on later part of the implementation.
NEXT STEPS
Wave iX team will share 10 Transcripts (5 for “Guest Relation” & 5 for Credit Card use.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 6
Leslie – Wave iX AI Agent
PROGRESS UPDATE
12:13:Scoping Call done with Parloa team on setting up AMP on Leslie’s Pool.
12/18:Intro call with client is conducted on
12/18:Listen mode data has been shared with Client
12/18:Wave iX: Figured out the pre-requisites i.e.
    Persona & Tone, Routing destination, forwarding to customers, LLM descriptions, API documentation. IT POC
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
IT PMO team will work with Client IT team for the details required for the integration .i.e. platform accessibility, FAQs, Diagrams, Persona, Routing destination, LLM descriptions.
Team aims to iron out the details around conversation flow, routing, FAQs, etc.
Team aims to begin work on connecting telephony, keeping required information in hand.
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 12/16 | Wave IX | In Progress
Telephony Integration | TBD | Wave IX | To-do
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 7
TiVo – Wave iX AI Agent
PROGRESS UPDATE
API access, Sales force access has been provisioned
We met internally to devise the next step for IVR automation.
We have the flows for the IVR.
We need to understand the detailed flows and corresponding conditional checks with Ops and CS.
Once above done, Tech team will explore API calls in details.
We had a session with Renjie and gave him access.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
CGC raised a concern of multiple duplicate records in reporting due to call deflection. | Reporting issues | CGC will keep participant ID same and wont change without informing Insight team Insight team will filter our the call legs with said participant ID. |  |  | Resolved
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Scoping for knowledge base and Salesforce integration. Internal meetup
For we need to share the E2E design documentation to the Client and tentative timelines for the implementation. Potentially end of March, 25
Requirement gathering from CS/Operations
Meeting with Palmer/TiVo about the solution
Critical Milestones | Due Date | Owner(s) | Status
Demo | 8/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 8
TiVo– Wave iX Chatbot
PROGRESS UPDATE
The API key, integration Manual has been shared by the partner with us 12/13
We do have TiVo’s send box access and Maven Key we can start exploring it
session with team on High-level Technical Requirements for the Integration
We are good to mimic deterministic flow and ML via NLP.
We have shared Decision Trees with the partner for review.
NEXT STEPS
Deep dive Session with Maven on Salesforce Integration and access provision, once Contract will be signed.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 12/16/2024 | Partner/Wave iX | Completed
General Discovery | TBD | Wave iX | To-do
Tech Discovery | TBD | Partner/Wave iX | To-do
Chat Integration | TBD | Wave iX | To-do
Evaluation | TBD | Wave iX | To-do
Production deployment | TBD | Wave iX | To-do
Postproduction Monitoring | TBD | Wave iX | To-do

## Slide 9
Modivcare - Wave IX Accent Localization
PROGRESS UPDATE
We have reviewed system requirements and good with them.
We are going with tech support LO, Bohol – PH and establish the KPIs AHT, CSAT.
SOW is in review with client followed by MSA contract signing.
NEXT STEPS
SOW review and endorsement from Client followed by.
MSA to get signed with Partner
Customized product for ibex
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Presales | 30 Dec 2025 | Ops/CS | In Progress
Deployment - POC | 1/6/2025 | Wave IX Team | To-do
Testing | 1/13/2025 | Wave IX Team | To-do
Go - Live | 1/13/2025 | Wave IX Team | To-do
Performance Measurement | 1/20/2025 | Wave IX Team | To-do

## Slide 10
Custom Ink – Wave iX AI Agent
PROGRESS UPDATE
A custom demo environment is handed over to CI.
Discussion completed with executives, signoff testing
Executives asked to revisit SOW in March 2025
NEXT STEPS
Executives asked to revisit SOW in March 2025
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 07/18/2024 | Owner / PMO | Completed
Telephony Integration | - | Owner / PMO | N/A
Listen Mode Enablement | 09/09/2024 | Wave IX Team | Completed
Listen Mode Analysis | 10/08/2024 | Eric | Completed
Performance Review and Evaluation | 11/18 | Client / PMO | In-Progress
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do

## Slide 11
Conifer – Wave IX Accent Localization
PROGRESS UPDATE
Pilot in Progress
Work performance data and feedback has been shared with Wave IX Accent team.
The problem In hand is that the tool(Krisp) worked well on the Female profile and doesn’t work well for the male profile.
Vendor advised to use a disclaimer script about the voice shaping to avoid questions from the customer about the roboticness of the call.
Vendor acknowledge and working on the fix in next release 12/16.
NEXT STEPS
Pilot to complete EO2024
Vendor acknowledge and working on the fix in next release 12/16..
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Vendor Communication | Jan 2024 | PMO / MT | Completed
Testers Alignment | 09/01/2024 | PMO | Completed
Test Stations Setup | 09/02/2024 | PMO / ITFS | Completed
AL App Deployment | 09/02/2024 | ITFS | Completed
Get approval to implement | 09/02/2024 | CS | Completed
Initiate Pilot | 09/04/2024 | CS / PMO / Wave IX | Completed
Results Analsys | 12/31 | CS / PMO / Wave IX | In-Progress

## Slide 12
UHC – Wave IX Accent Preservation
PROGRESS UPDATE
Client agrees to have Preserve mode deployed on the Production (No Pilot)
Installation on PH (Davao, Bohol) done on around 144 Workstations.
Weekly Monitoring session with Vendor and Ops for the progress.
NPS score and performance started deteriorating.
Krisp to push another improves release.
CS decided to remove preserve from larger population.
Only 10 agents to kept active on Preserve.
Improved version deployed 12/19.
Production use tested and relaunched 12/20
Initial testing results seem to be much improved.
NEXT STEPS
Monitoring the performance via call recordings on daily basis.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo to the Client | 11/25 | Wave iX/Client | Completed
Client Approval | 11/25 | Client | Completed
Testing (Pilot) | 11/28 | Wave iX | Completed
Deployment | 12/3 | Wave iX | Completed
Monitoring | 12/13 | Wave iX | In-Progress

## Slide 13
Other 3rd Party Tools
3rd Party Partner | Wave iX Solution | Description
Envoy Visitor | Not under Wave iX | Envoy Visitors is a cloud based electronic visitor management system that streamlines the check-in process, enhancing security and visitor experience by digitizing sign-ins and tracking in workplaces.

## Slide 14
Envoy – Electronic Visitor Management Solution
PROGRESS UPDATE
A digital replacement of conventional paper based system.
Initially deployed to 4 ibex sites last year as part of Google VoVo audit.
It was planned to expand to other sites in future as well.
Currently we are using Premium licenses.
Amazon compliance audit also mandated to use EVMS on all amazon sites.
We have reviewed and opted for its Enterprise version due to more security features.
Pricing approval in progress.
Licenses and equipment procured
NEXT STEPS
Site configurations, hardware deployment
Go-Live.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Hardware availability in PH and PK | Delay | Needs to be hand carried from US | TBD | PMO / Procurement | Pending
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initiate Vendor Communication | March 2024 | PMO / Procurement | Completed
Feature and Pricing Review | April 2024 | PMO / Procurement / Compliance | Completed
Pricing Negotiation | July 2024 | Procurement | Completed
Gather Site and Regional Approvals | August 2024 | PMO | Completed
Gather Management Approval | September 2024 | Procurement | Completed
Place Orders | October 2024 | Procurement | Completed
Deployment | December 2024 | PMO / ITFS | Pending
3rd Party Tools

## Slide 15
Thank you.