## Slide 1
Life Cycle
& 3rd Party Tools

## Slide 2
Mint Mobile – Wave iX Agent AI
PROGRESS UPDATE
The SIP trunk information were shared with Wave IX team.
successfully configures the SIP trunk setup at
successful E2E test call on the Mint IVR.
We came across BOT configuration issue, However, we have found out the work around for the successful call flow and our Go-live.
Ibex QA team did run a complete test cases with successfully and give a go-ahead.
We meet Mint's telephony team for demonstrations on the implementation and they are good with the architecture.
We are aiming to run the BOT IVR on 1/20 for couple of hours for the production test.
NEXT STEPS
Session with QA team on the 1/17.
Client Demo on E2E call 1/17.
Go-Live 1/20
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Delayed Implementation | Bad impact on client in terms of implementation expertise | Parloa engaged on top priority to devise solution. | TBD | Wave iX | In-Progress
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | 1/14 | Wave IX | Completed
Back-end system integration | TBD | Wave IX | Completed
Testing & Pre Go-:Live | 1/17 | QA | In Progress
Go-:Live | 1/20 | Operations | To-do

## Slide 3
RedRoof Inn – Wave iX Translate
PROGRESS UPDATE
We conducted multiple session with Red Roof Inn Amazon Connect team to establish the trunk with Wave IX Translate.
We are able to confirm Queues/routing decisions along with TFN and numbers o and from Translate.
We successfully resolved issues on a session with client team to test E2E translate call
Call Routing has been configured from Wave iX Translate to Amazon Connect & Vice versa.
We did a successful session with Spanish caller to conduct E2E test call on staging environment
We are aiming to have another session with more Reps 1/17 for better coverage of scenarios before going live
Production agents users are created to test complete E2E Call users.
We give heads up for pushing the changes to the production environment.
Training with Ops is like to come once testing is done.
NEXT STEPS
1/17 :Testing session with Production agents on staging environment before go live.
1/20: Agent/Ops training on the Wave iX translate.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Discovery | 11/15 | Wave iX | Completed
Planning | 12/6 | Wave iX | Completed
Tech Discovery | 12/19 | Wave iX | Completed
Design | TBD | Wave iX | Completed
Implementation | TBD | Wave iX | Completed
Training & Testing | TBD | Ops/CS | In-Progress
Deployment | TBD | Wave iX | To-do

## Slide 4
Leslie – Wave iX AI Agent
PROGRESS UPDATE
Leslie’s pool team has shared the API documentation for CRM.
Client able to share use cases and corresponding expected responses
The users for API has been created for Wave iX folks.
We have requested Operations to get the details for the flows in-scoped in phase 1 MVP
    We have requested Genesys team to establish SIP trunk for Leslie’s pool.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Follow up with telephony team on the SIP trunk status.
Wave iX will continue to work with technical deliverables that supports in later part of the implementations.
Team aims to iron out the details around conversation flow, routing, FAQs, etc with Operations team
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | TBD | Wave IX | Completed
Documentation | TBD | Wave IX | In Progress
Telephony Integration | TBD | Wave IX | In-Progress
Back-end system integration | TBD | Wave IX | In-Progress
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 5
TiVo– Wave iX Chatbot
PROGRESS UPDATE
Decision trees have been shared with the partner, and they are currently working on them.
The initial staging chatbot has been provided to TiVo for feedback.
TiVo has requested a quick Q&A session with the partner.
The Maven chatbot has been integrated into the staging TiVo Support Center site.
The partner has requested to ingest the production knowledge base (KB) into the chatbot for improved scenario coverage and enhanced model training.
TiVo has created a production user, and the partner will proceed with ingesting the chatbot.
After the production KB is ingested, a full QA test execution cycle will be conducted.
Timelines have been established, with the aim to go live by February 1st
NEXT STEPS
Partner to share the update on ingesting the Production KB to chat bot
QA will start executing a full testing cycle
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 12/16/24 | Partner/Wave iX | Completed
General Discovery | 1/06 | Wave iX | Completed
Tech Discovery | 1/11 | Partner/Wave iX | Completed
Chat Integration | 1/17 | Wave iX | In-Progress
Evaluation & Testing | 1/28 | Wave iX | To-do
Production deployment | 2/1 | Wave iX | To-do
Postproduction Monitoring | TBD | Wave iX | To-do

## Slide 6
TiVo – Wave iX AI Agent
PROGRESS UPDATE
The IVR flows have been received from Genesys.
The timeline has been communicated to the client.
The end-to-end (E2E) design document has been shared with the client.
A session with Operations is planned to discuss the use cases included in Phase 1 of the MVP.
Based on the above, the API endpoint needs to be identified.
If write access is required, a request will need to be submitted to the client.
FAQs also need to be obtained from Operations.
A session with Renjie has been conducted, and access has been provided.
For telephony integration, we have requested to setup a trunk for TiVo.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
CGC raised a concern of multiple duplicate records in reporting due to call deflection. | Reporting issues | CGC will keep participant ID same and wont change without informing Insight team Insight team will filter our the call legs with said participant ID. |  |  | Resolved
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Session with Client Services, Ops and Wasiq on API related queries 1/17
Critical Milestones | Due Date | Owner(s) | Status
Demo | 8/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | In-Progress
Telephony Integration | TBD | Wave IX | In-Progress
Back-end system integration | TBD | Wave IX | In-Progress
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 7
Modivcare - Wave IX Accent Localization
PROGRESS UPDATE
We have reviewed system requirements and good with them.
We are going with tech support LO, Bohol – PH and establish the KPIs AHT, CSAT.
SOW is in review with client followed by MSA contract signing. And will be done by 1/22.
We can then deploy the POC on random machines and let the POC run for a week.
We can then go for the full campaign deployment max by 2/1
NEXT STEPS
Waiting for SOW and MSA.
TO check the pre-requisites for the installation and partner connectivity with Ibex.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Presales ( | 1/22 | Ops/CS | In Progress
Deployment - POC | 1/23 | Wave IX Team | To-do
Testing | 1/29 | Wave IX Team | To-do
Go - Live | 2/1 | Wave IX Team | To-do
Performance Measurement | 2/8 | Wave IX Team | To-do

## Slide 8
RedRoof Inn – Wave iX AI Agent
PROGRESS UPDATE
Retro Listen mode was requested to Wave iX AI agent for listening 500 calls on the box space.
Ibex has provisioned 500calls to Wave iX AI agent
Post listen mode data presented to CS.
CS opted for automating “Guest Relation” use case for the MVP. As it has less Credit card need.
We will cover CC based use case on later part of the implementation.
NEXT STEPS
Wave iX team will share 10 Transcripts (5 for “Guest Relation” & 5 for Credit Card use.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 9
Custom Ink – Wave iX AI Agent
PROGRESS UPDATE
A custom demo environment is handed over to CI.
Discussion completed with executives, signoff testing
Executives asked to revisit SOW in March 2025
NEXT STEPS
Executives asked to revisit SOW in March 2025
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 07/18/2024 | Owner / PMO | Completed
Telephony Integration | - | Owner / PMO | N/A
Listen Mode Enablement | 09/09/2024 | Wave IX Team | Completed
Listen Mode Analysis | 10/08/2024 | Eric | Completed
Performance Review and Evaluation | 11/18 | Client / PMO | In-Progress
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do

## Slide 10
Conifer – Wave IX Accent Localization
PROGRESS UPDATE
Pilot in Progress
Work performance data and feedback has been shared with Wave IX Accent team.
The problem In hand is that the tool(Krisp) worked well on the Female profile and doesn’t work well for the male profile.
Vendor advised to use a disclaimer script about the voice shaping to avoid questions from the customer about the roboticness of the call.
Vendor acknowledge and working on the fix in next release 12/16.
NEXT STEPS
Pilot to complete EO2024
Vendor acknowledge and working on the fix in next release 12/16..
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Vendor Communication | Jan 2024 | PMO / MT | Completed
Testers Alignment | 09/01/2024 | PMO | Completed
Test Stations Setup | 09/02/2024 | PMO / ITFS | Completed
AL App Deployment | 09/02/2024 | ITFS | Completed
Get approval to implement | 09/02/2024 | CS | Completed
Initiate Pilot | 09/04/2024 | CS / PMO / Wave IX | Completed
Results Analsys | 12/31 | CS / PMO / Wave IX | In-Progress

## Slide 11
UHC – Wave IX Accent Preservation
PROGRESS UPDATE
Client agrees to have Preserve mode deployed on the Production (No Pilot)
Installation on PH (Davao, Bohol) done on around 144 Workstations.
Weekly Monitoring session with Vendor and Ops for the progress.
NPS score and performance started deteriorating.
Krisp to push another improves release.
CS decided to remove preserve from larger population.
Only 10 agents to kept active on Preserve.
Improved version deployed 12/19.
Production use tested and relaunched 12/20
Initial testing results seem to be much improved.
NEXT STEPS
Monitoring the performance via call recordings on daily basis.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo to the Client | 11/25 | Wave iX/Client | Completed
Client Approval | 11/25 | Client | Completed
Testing (Pilot) | 11/28 | Wave iX | Completed
Deployment | 12/3 | Wave iX | Completed
Monitoring | 12/13 | Wave iX | In-Progress

## Slide 12
Other 3rd Party Tools
3rd Party Partner | Wave iX Solution | Description
Envoy Visitor | Not under Wave iX | Envoy Visitors is a cloud based electronic visitor management system that streamlines the check-in process, enhancing security and visitor experience by digitizing sign-ins and tracking in workplaces.

## Slide 13
Envoy – Electronic Visitor Management Solution
PROGRESS UPDATE
A digital replacement of conventional paper based system.
Initially deployed to 4 ibex sites last year as part of Google VoVo audit.
It was planned to expand to other sites in future as well.
Currently we are using Premium licenses.
Amazon compliance audit also mandated to use EVMS on all amazon sites.
We have reviewed and opted for its Enterprise version due to more security features.
Pricing approval in progress.
Licenses and equipment procured
NEXT STEPS
Site configurations, hardware deployment
Go-Live.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Hardware availability in PH and PK | Delay | Needs to be hand carried from US | TBD | PMO / Procurement | Pending
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initiate Vendor Communication | March 2024 | PMO / Procurement | Completed
Feature and Pricing Review | April 2024 | PMO / Procurement / Compliance | Completed
Pricing Negotiation | July 2024 | Procurement | Completed
Gather Site and Regional Approvals | August 2024 | PMO | Completed
Gather Management Approval | September 2024 | Procurement | Completed
Place Orders | October 2024 | Procurement | Completed
Deployment | December 2024 | PMO / ITFS | Pending
3rd Party Tools

## Slide 14
Thank you.