## Slide 1
Life Cycle
& 3rd Party Tools

## Slide 2
Mint Mobile – Wave iX Agent AI
PROGRESS UPDATE
Mint Project phase 2 plan developed and shared across board.
  In Phase 2 aiming to Automate Business critical Use case(s) + extending the FAQs piece
PMO/Ops collectively worked on Use case details (steps)
Use case review session with Ops and CS and.
Linear flow diagram developed. Waiting for the API end points
Requested Mint folks to provide API end point for the use cases
NEXT STEPS
Followed up with client
Once API details available, E2E diagram needs to be shared with Wave iX for the BOT development..
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Delayed Implementation | Bad impact on client in terms of implementation expertise | Parloa engaged on top priority to devise solution. | TBD | Wave iX | In-Progress
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20/24 | Wave IX | Completed
Kick Off | 11/20/24 | Wave IX | Completed
Discovery | 11/25/24 | Wave IX | Completed
Telephony Integration | 11/14/24 | Wave IX | Completed
Bot Configuration (Setup KB, API and Routes) |  | Wave IX | In-Progress
Back-end system integration |  | Wave IX | In-Progress
Deploy Phase 1 - MVP | 01/15/25 | Wave IX | Completed
User Acceptance Testing | 01/20/25 | Wave IX Operations | Completed
Go-Live | 01/22/25 | Operations | Completed
Deploy Phase 2 – Use Cases | 2/21/25 | Wave IX | To-do
User Acceptance Testing | 3/1/25 | Wave IX Operations | To-do
Go-Live | 3/07/25 | Operations | To-do

## Slide 3
Leslie – Wave iX AI Agent
PROGRESS UPDATE
Telephony integration between Wave iX and Genesys completed and validated.
API documentation along with test API provided by Leslie’s client.
Ops have shared the Use case scenarios against 4 intents.
Wave iX team currently working on Bot building and KB integration.
    Wave iX team testing APIs and validating endpoints in parallel.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Team aims to iron out the details around conversation flow, routing, FAQs, etc. with Operations team.
Leslie’s client to provide Boomi API for production use to mask irrelevant parameters.
Setting up first intent automation in Phase 1 as MVP.
Review and feedback analysis of Phase 1.
Deployment of remaining intent automation as part of Phase 2.
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20/24 | Wave IX | Completed
Kick Off | 11/20/24 | Wave IX | Completed
Discovery | 02/03/25 | Wave IX | Completed
Telephony Integration | 01/25/25 | Wave IX | Completed
Bot Configuration (Setup KB, API and Routes) | 02/03/25 | Wave IX | In-Progress
Back-end system integration | 02/10/25 | Wave IX | In-Progress
Deploy Phase 1 - MVP | 02/18/25 | Wave IX | To-do
User Acceptance Testing | 02/21/25 | Wave IX Operations | To-do
Go-Live | 02/26/25 | Operations | To-do
Deploy Phase 2 – Use Cases | 03/15/25 | Wave IX | To-do
User Acceptance Testing | 03/20/25 | Wave IX Operations | To-do
Go-Live | 03/26/25 | Operations | To-do

## Slide 4
TiVo – Wave iX AI Agent
PROGRESS UPDATE
The IVR flows have been received from Genesys.
The timeline has been communicated to the client.
The end-to-end (E2E) design document has been shared with the client.
Ops have shared detailed scenarios for automation use cases.
Based on the above, the API endpoint needs to be identified.
Telephony integration between Genesys and Wave iX is in progress.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
CGC raised a concern of multiple duplicate records in reporting due to call deflection. | Reporting issues | CGC will keep participant ID same and wont change without informing Insight team Insight team will filter our the call legs with said participant ID. |  |  | Resolved
Bot building and KB integration.
MVP deployment
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 08/20/24 | Wave IX | Completed
Kick Off | 11/20/24 | Wave IX | Completed
Discovery | 11/25/25 | Wave IX | Completed
Telephony Integration | 01/31/25 | Wave IX | In-Progress
Bot Configuration (Setup KB, API and Routes) | TBD | Wave IX | To-do
Back-end system integration | TBD | Wave IX | To-do
Deploy Phase 1 - MVP | TBD | Wave IX | To-do
User Acceptance Testing | TBD | Wave IX Operations | To-do
Go-Live | TBD | Operations | To-do
Deploy Phase 2 – Use Cases | TBD | Wave IX | To-do
User Acceptance Testing | TBD | Wave IX Operations | To-do
Go-Live | TBD | Operations | To-do

## Slide 5
RedRoof Inn – Wave iX AI Agent
PROGRESS UPDATE
Retro Listen mode was requested to Wave iX AI agent for listening 500 calls on the box space.
Ibex has provisioned 500calls to Wave iX AI agent
Post listen mode data presented to CS.
CS opted for automating “Guest Relation” use case for the MVP. As it has less Credit card need.
We will cover CC based use case on later part of the implementation.
NEXT STEPS
Wave iX team will share 10 Transcripts (5 for “Guest Relation” & 5 for Credit Card use.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20/24 | Wave IX | Completed
Kick Off | 11/20/24 | Wave IX | Completed
Discovery | 11/25/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | To-do
Bot Configuration (Setup KB, API and Routes) | TBD | Wave IX | To-do
Back-end system integration | TBD | Wave IX | To-do
Deploy Phase 1 - MVP | TBD | Wave IX | To-do
User Acceptance Testing | TBD | Wave IX Operations | To-do
Go-Live | TBD | Operations | To-do
Deploy Phase 2 – Use Cases | TBD | Wave IX | To-do
User Acceptance Testing | TBD | Wave IX Operations | To-do
Go-Live | TBD | Operations | To-do

## Slide 6
Custom Ink – Wave iX AI Agent
PROGRESS UPDATE
A custom demo environment is handed over to CI.
Discussion completed with executives, signoff testing
Executives asked to revisit SOW in March 2025
NEXT STEPS
Executives asked to revisit SOW in March 2025
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 07/18/2024 | Owner / PMO | Completed
Telephony Integration | - | Owner / PMO | N/A
Listen Mode Enablement | 09/09/2024 | Wave IX Team | Completed
Listen Mode Analysis | 10/08/2024 | Eric | Completed
Performance Review and Evaluation | 11/18 | Client / PMO | In-Progress
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do

## Slide 7
RedRoof Inn – Wave iX Translate
PROGRESS UPDATE
We conducted multiple session with Red Roof Inn Amazon Connect team to establish the trunk with Wave IX Translate.
Call Routing has been configured from Wave iX Translate to Amazon Connect & Vice versa.
We did a successful session with Spanish caller to conduct E2E test call on staging environment
UAT conducted with 2 agents with multiple Spanish calls.
Spanish Queue agents have also been assigned low priority English calls to maintain agent occupancy.
RTT has been live since 01/22 without any concerns.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20/24 | Wave IX | Completed
Kick Off | 11/15/24 | Wave IX | Completed
Discovery | 12/19/25 | Wave IX | Completed
Telephony Integration | 01/10/25 | Wave IX | To-do
RTT Agent Designing | 01/15/25 | Wave IX | To-do
User Acceptance Testing | 01/17/25 | Wave IX Operations | To-do
Go-Live | 01/22/25 | Operations | To-do
Design refinements for RRI. Jamaica

## Slide 8
TiVo– Wave iX Chatbot
PROGRESS UPDATE
Chat handoff feature delivered and demonstrated to client.
Internal UAT done with Operations on E2E testing of Chatbot before go-live.
Major critical fixes are done. QA will continue to execute test(s) and report the issues.
We have all pre-requisites set for the go-live.
1/31 6PM PST is set for Go-live. Formal notification is rolled out to all stakeholders.
NEXT STEPS
Go-Live 1/31
Monitoring for a week between 2/1 -2/5
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 12/16/24 | Partner/Wave iX | Completed
General Discovery | 1/06 | Wave iX | Completed
Tech Discovery | 1/11 | Partner/Wave iX | Completed
Chat Integration | 1/17 | Wave iX | Completed
Evaluation & Testing | 1/28 | Wave iX | Completed
Production deployment | 2/1 | Wave iX | To-do
Postproduction Monitoring | TBD | Wave iX | To-do

## Slide 9
Modivcare - Wave IX Accent Localization
PROGRESS UPDATE
We have reviewed system requirements and good with them.
We are going with tech support LO, Bohol – PH and establish the KPIs AHT, CSAT.
SOW is in review with client followed by MSA contract signing. And will be done by 2/05/25.
We can then deploy the POC on random machines and let the POC run for a week.
We can then go for the full campaign deployment max by 2/15/25
NEXT STEPS
Waiting for SOW and MSA.
TO check the pre-requisites for the installation and partner connectivity with Ibex.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Presales | 1/22 | Ops/CS | In Progress
Deployment - POC | 02/10/25 | Wave IX Team | To-do
Testing | 02/11/25 | Wave IX Team | To-do
Go - Live | 02/15/25 | Wave IX Team | To-do
Performance Measurement | 02/28/25 | Wave IX Team | To-do

## Slide 10
Conifer – Wave IX Accent Localization
PROGRESS UPDATE
Pilot in Progress
Work performance data and feedback has been shared with Wave IX Accent team.
The problem In hand is that the tool(Krisp) worked well on the Female profile and doesn’t work well for the male profile.
Vendor advised to use a disclaimer script about the voice shaping to avoid questions from the customer about the roboticness of the call.
Vendor acknowledge and working on the fix in next release 12/16.
Results have not been very promising with Philippines version hence leadership has decided to end the POC.
NEXT STEPS
Pilot to complete EO2024
Vendor acknowledge and working on the fix in next release 12/16..
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Vendor Communication | Jan 2024 | PMO / MT | Completed
Testers Alignment | 09/01/2024 | PMO | Completed
Test Stations Setup | 09/02/2024 | PMO / ITFS | Completed
AL App Deployment | 09/02/2024 | ITFS | Completed
Get approval to implement | 09/02/2024 | CS | Completed
Initiate Pilot | 09/04/2024 | CS / PMO / Wave IX | Completed
Results Analsys | 12/31 | CS / PMO / Wave IX | In-Progress

## Slide 11
UHC – Wave IX Accent Preservation
PROGRESS UPDATE
Client agrees to have Preserve mode deployed on the Production (No Pilot)
Installation on PH (Davao, Bohol) done on around 144 Workstations.
Weekly Monitoring session with Vendor and Ops for the progress.
NPS score and performance started deteriorating.
Krisp to push another improves release.
CS decided to remove preserve from larger population.
Only 10 agents to kept active on Preserve.
Improved version deployed 12/19.
Production use tested and relaunched 12/20
Initial testing results seem to be much improved.
POC has been halted due to negative feedback.
NEXT STEPS
Looking forward to another Partner onboarding for same kind of solution.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo to the Client | 11/25 | Wave iX/Client | Completed
Client Approval | 11/25 | Client | Completed
Testing (Pilot) | 11/28 | Wave iX | Completed
Deployment | 12/3 | Wave iX | Completed
Monitoring | 12/13 | Wave iX | In-Progress

## Slide 12
Other 3rd Party Tools
3rd Party Partner | Wave iX Solution | Description
Envoy Visitor | Not under Wave iX | Envoy Visitors is a cloud based electronic visitor management system that streamlines the check-in process, enhancing security and visitor experience by digitizing sign-ins and tracking in workplaces.

## Slide 13
Envoy – Electronic Visitor Management Solution
PROGRESS UPDATE
A digital replacement of conventional paper based system.
Initially deployed to 4 ibex sites last year as part of Google VoVo audit.
It was planned to expand to other sites in future as well.
Currently we are using Premium licenses.
Amazon compliance audit also mandated to use EVMS on all amazon sites.
We have reviewed and opted for its Enterprise version due to more security features.
Pricing approval in progress.
Licenses and equipment procured
Deployment in Progress and targeted to be completed by mid of Feb 25
NEXT STEPS
Site configurations, hardware deployment
Go-Live.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Hardware availability in PH and PK | Delay | Needs to be hand carried from US | TBD | PMO / Procurement | Resolved
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initiate Vendor Communication | March 2024 | PMO / Procurement | Completed
Feature and Pricing Review | April 2024 | PMO / Procurement / Compliance | Completed
Pricing Negotiation | July 2024 | Procurement | Completed
Gather Site and Regional Approvals | August 2024 | PMO | Completed
Gather Management Approval | September 2024 | Procurement | Completed
Place Orders | October 2024 | Procurement | Completed
Deployment | February 2024 | PMO / ITFS | In-Progress
3rd Party Tools

## Slide 14
Thank you.