## Slide 1
Life Cycle
& 3rd Party Tools

## Slide 2
Authenticate & Automate
AI-driven voice and IVR automation platform that streamlines customer service by automating routine tasks, enhancing efficiency, and improving customer experiences.
Wave iX AI Agent
Active Opportunities:
Custom Ink
Leslie
Redroof Inc.
TiVo
Mint Mobile
Pipeline Opportunities :
Transcard
Wave iX Translate
Active Opportunities:
Red Roof Inn
Pipeline Opportunities :
Modivcare,
Saferide
UPS
Transcard
Lyft
Square Trade
Mercedes Benz

## Slide 3
Mint Mobile – Wave iX Agent AI
PROGRESS UPDATE
Followed up by with client on endorsing the changes on client's platform. waiting on client's approval on the changes.
Test Cycle is performed & reviewed Test report with Wave iX team on 1/3 to get aligned.
Security approval is secured on Customer conversation(s) .
Partner raised the need of having trunk setup details.
NEXT STEPS
We have requested client for an interactive session to discuss below
- Figure out if yaml or another format works for the configurational changes.
        - we need to ask client for Sim activation flow, Plan information Flow
- We need to get Least /Off production window for changes. tentatively between 1/9 and 1/13
- client's approval on the changes
- Trunk Setup details with the client.
Need to send recordings to Partner for model learning. Security and Alfy are good, Ops will share 50 sample recordings to us.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Delayed Implementation | Bad impact on client in terms of implementation expertise | Parloa engaged on top priority to devise solution. | TBD | Wave iX | In-Progress
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | In Progress
Testing & Pre Go-:Live | TBD | Operations | In Progress
Go-:Live | TBD | Operations | To-do

## Slide 4
RedRoof Inn – Wave iX Translate
PROGRESS UPDATE
Wave iX is still devising a solution to segregate “Guest Relations” and “Booking” calls.
Once solution will be devised, wave iX will develop configurations that will contain some changes to the platform.
Wave iX team is understanding integration piece internally before having a session.
Wave iX team is setting up Lab internally and share once this is done.
We reviewed Amazon connect documentation of RRI and shared with Wave iX team to review how flows are established in AWS Connect.
CS has shared the sample transcripts.
We need to discover Inbound Numbers, Staging environment, chained Certificates, IP whitelisting from client for the integrations
2/15 is the Go-Live date
NEXT STEPS
Tech session with client on connectivity between Amazon connect and Wave iX translate.
Follow up on Lab setup, DID and the solutions for segregating the guest relations and
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Discovery | 11/15 | Wave iX | Completed
Planning | 12/6 | Wave iX | Completed
Tech Discovery | 12/19 | Wave iX | In-Progress
Design | TBD | Wave iX | In-Progress
Implementation | TBD | Wave iX | In-Progress
Training & Testing | TBD | Ops/CS | To-do
Deployment | TBD | Wave iX | To-do

## Slide 5
RedRoof Inn – Wave iX AI Agent
PROGRESS UPDATE
Retro Listen mode was requested to Wave iX AI agent for listening 500 calls on the box space.
Ibex has provisioned 500calls to Wave iX AI agent
Post listen mode data presented to CS.
CS opted for automating “Guest Relation” use case for the MVP. As it has less Credit card need.
We will cover CC based use case on later part of the implementation.
NEXT STEPS
Wave iX team will share 10 Transcripts (5 for “Guest Relation” & 5 for Credit Card use.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 6
Leslie – Wave iX AI Agent
PROGRESS UPDATE
Scoping Call done with Wave iX team on setting up AMP on Leslie’s Pool.
Intro call with client is conducted
Listen mode data has been shared with Client
    Persona & Tone, Routing destination, forwarding to customers, LLM descriptions, API documentation. IT POC
    Client able to share use cases and corresponding expected responses
    Security personnel is concerned about exposing PII data to us. they are looking for a way to expose data to us.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Client personnel will come up with the proposed solution of sharing data with us.
Wave iX will continue to work with Client IT team for the details further required for the integration .i.e. platform accessibility, FAQs, Diagrams, Persona, Routing destination, LLM descriptions.
Team aims to iron out the details around conversation flow, routing, FAQs, etc.
Team aims to begin work on connecting telephony, keeping required information in hand.
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 12/16 | Wave IX | In Progress
Telephony Integration | TBD | Wave IX | To-do
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 7
TiVo – Wave iX AI Agent
PROGRESS UPDATE
We met internally to devise the next step for IVR automation.
We have the flows for the IVR.
Time line has been shared with the Client
E2E Design document has been shared with the Client.
Considering resources availability we need to check if we can get the planning phase done.
We can review what is missing in the technical requirements(pre-requisites) and proceed ahead
We had a session with Renjie and gave him access.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
CGC raised a concern of multiple duplicate records in reporting due to call deflection. | Reporting issues | CGC will keep participant ID same and wont change without informing Insight team Insight team will filter our the call legs with said participant ID. |  |  | Resolved
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Setup a session with Client Services, Ops and Wasiq on API related queries 1/10
Critical Milestones | Due Date | Owner(s) | Status
Demo | 8/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 8
TiVo– Wave iX Chatbot
PROGRESS UPDATE
We have shared Decision trees with the partner.
Joint Tech session with client on integrating Maven solution with Tivo Salesforce
Partner walk us through the integration between Maven & Salesforce.
High level Timeline has been shared with the Client. however detailed plan will be shared with them later on.
NEXT STEPS
Partner will share the testing status by 1/10.
Client to create salesforce login credentials for Our partner
Partner to set up and test the connected app in Salesforce once he receives access.
Justin to prepare next steps for getting the chatbot on the site and share the scripts for implementation.
Project Plan for Wave iX Virtual Chatbot template for TiVo
Internal PMO review -> Wave iX team -> then publish with Partner
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 12/16/2024 | Partner/Wave iX | Completed
General Discovery | TBD | Wave iX | Completed
Tech Discovery | TBD | Partner/Wave iX | Completed
Chat Integration | TBD | Wave iX | In-Progress
Evaluation | TBD | Wave iX | To-do
Production deployment | TBD | Wave iX | To-do
Postproduction Monitoring | TBD | Wave iX | To-do

## Slide 9
Modivcare - Wave IX Accent Localization
PROGRESS UPDATE
We have reviewed system requirements and good with them.
We are going with tech support LO, Bohol – PH and establish the KPIs AHT, CSAT.
SOW is in review with client followed by MSA contract signing.
NEXT STEPS
SOW review and endorsement from Client followed by.
MSA to get signed with Partner
Customized product for ibex
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Presales | 30 Dec 2025 | Ops/CS | In Progress
Deployment - POC | 1/6/2025 | Wave IX Team | To-do
Testing | 1/13/2025 | Wave IX Team | To-do
Go - Live | 1/13/2025 | Wave IX Team | To-do
Performance Measurement | 1/20/2025 | Wave IX Team | To-do

## Slide 10
Custom Ink – Wave iX AI Agent
PROGRESS UPDATE
A custom demo environment is handed over to CI.
Discussion completed with executives, signoff testing
Executives asked to revisit SOW in March 2025
NEXT STEPS
Executives asked to revisit SOW in March 2025
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 07/18/2024 | Owner / PMO | Completed
Telephony Integration | - | Owner / PMO | N/A
Listen Mode Enablement | 09/09/2024 | Wave IX Team | Completed
Listen Mode Analysis | 10/08/2024 | Eric | Completed
Performance Review and Evaluation | 11/18 | Client / PMO | In-Progress
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do

## Slide 11
Conifer – Wave IX Accent Localization
PROGRESS UPDATE
Pilot in Progress
Work performance data and feedback has been shared with Wave IX Accent team.
The problem In hand is that the tool(Krisp) worked well on the Female profile and doesn’t work well for the male profile.
Vendor advised to use a disclaimer script about the voice shaping to avoid questions from the customer about the roboticness of the call.
Vendor acknowledge and working on the fix in next release 12/16.
NEXT STEPS
Pilot to complete EO2024
Vendor acknowledge and working on the fix in next release 12/16..
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Vendor Communication | Jan 2024 | PMO / MT | Completed
Testers Alignment | 09/01/2024 | PMO | Completed
Test Stations Setup | 09/02/2024 | PMO / ITFS | Completed
AL App Deployment | 09/02/2024 | ITFS | Completed
Get approval to implement | 09/02/2024 | CS | Completed
Initiate Pilot | 09/04/2024 | CS / PMO / Wave IX | Completed
Results Analsys | 12/31 | CS / PMO / Wave IX | In-Progress

## Slide 12
UHC – Wave IX Accent Preservation
PROGRESS UPDATE
Client agrees to have Preserve mode deployed on the Production (No Pilot)
Installation on PH (Davao, Bohol) done on around 144 Workstations.
Weekly Monitoring session with Vendor and Ops for the progress.
NPS score and performance started deteriorating.
Krisp to push another improves release.
CS decided to remove preserve from larger population.
Only 10 agents to kept active on Preserve.
Improved version deployed 12/19.
Production use tested and relaunched 12/20
Initial testing results seem to be much improved.
NEXT STEPS
Monitoring the performance via call recordings on daily basis.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo to the Client | 11/25 | Wave iX/Client | Completed
Client Approval | 11/25 | Client | Completed
Testing (Pilot) | 11/28 | Wave iX | Completed
Deployment | 12/3 | Wave iX | Completed
Monitoring | 12/13 | Wave iX | In-Progress

## Slide 13
Other 3rd Party Tools
3rd Party Partner | Wave iX Solution | Description
Envoy Visitor | Not under Wave iX | Envoy Visitors is a cloud based electronic visitor management system that streamlines the check-in process, enhancing security and visitor experience by digitizing sign-ins and tracking in workplaces.

## Slide 14
Envoy – Electronic Visitor Management Solution
PROGRESS UPDATE
A digital replacement of conventional paper based system.
Initially deployed to 4 ibex sites last year as part of Google VoVo audit.
It was planned to expand to other sites in future as well.
Currently we are using Premium licenses.
Amazon compliance audit also mandated to use EVMS on all amazon sites.
We have reviewed and opted for its Enterprise version due to more security features.
Pricing approval in progress.
Licenses and equipment procured
NEXT STEPS
Site configurations, hardware deployment
Go-Live.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Hardware availability in PH and PK | Delay | Needs to be hand carried from US | TBD | PMO / Procurement | Pending
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initiate Vendor Communication | March 2024 | PMO / Procurement | Completed
Feature and Pricing Review | April 2024 | PMO / Procurement / Compliance | Completed
Pricing Negotiation | July 2024 | Procurement | Completed
Gather Site and Regional Approvals | August 2024 | PMO | Completed
Gather Management Approval | September 2024 | Procurement | Completed
Place Orders | October 2024 | Procurement | Completed
Deployment | December 2024 | PMO / ITFS | Pending
3rd Party Tools

## Slide 15
Thank you.