## Slide 1
Life Cycle
& 3rd Party Tools

## Slide 2
Authenticate & Automate
AI-driven voice and IVR automation platform that streamlines customer service by automating routine tasks, enhancing efficiency, and improving customer experiences.
WaveIX AI Agent
Active Opportunities:
Custom Ink
Leslie
Redroof Inc.
TiVo
Mint Mobile
Pipeline Opportunities :
Transcard
WaveIX Translate
Active Opportunities:
Red Roof Inn
Pipeline Opportunities :
Modivcare,
Saferide
UPS
Transcard
Lyft
Square Trade
Mercedes Benz

## Slide 3
Mint Mobile – WaveIX Agent AI
PROGRESS UPDATE
Additional requested urls are whitelisted WaveIX AI needs to verify and confirm.
WaveIX team has requested for the API key to proceed with the authentication.
NEXT STEPS
WaveIX to check the access for the additional requested URLs. Once done we will be able to proceed with the next steps.
WaveIX team is working on delivering the MVP with sophisticating Routing and FAQs
Telephony & Backend System integration.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Delayed Implementation | Bad impact on client in terms of implementation expertise | Parloa engaged on top priority to devise solution. | TBD | WaveiX | In-Progress
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 4
RedRoof Inn – WaveIX Translate
PROGRESS UPDATE
Automation for “Guest Relations” for automation & forward reservations calls to the reps.
Looking for a way to segregate PCI and Non-PCI call. Rengie proposed a solution, which needs to be reviewed by client.
Sample (10) transcripts to share with WaveIX Translate.
Complete Binding Agreement and then finalize project plan/launch
NEXT STEPS
WaveIX to share the DID for the “Guest relations” for segregating the routes.
Complete Binding Agreement and then finalize project plan/launch.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Discovery | 11/15 | WaveIX | Completed
Planning | 12/6 | WaveIX | Completed
Tech Discovery | 12/19 | WaveIX | In-Progress
Design | TBD | WaveIX | To-do
Implementation | TBD | WaveIX | To-do
Training & Testing | TBD | Ops/CS | To-do
Deplooyment | TBD | WaveIX | To-do

## Slide 5
RedRoof Inn – WaveIX AI Agent
PROGRESS UPDATE
Retro Listen mode was requested to WaveiX AI agent for listening 500 calls on the box space.
Ibex has provisioned 500calls to WaveiX AI agent
Post listen mode data presented to CS.
CS opted for automating “Guest Relation” use case for the MVP. As it has less Credit card need.
We will cover CC based use case on later part of the implementation.
NEXT STEPS
WaveIX team will share 10 Transcripts (5 for “Guest Relation” & 5 for Credit Card use.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 08/25/2024 | Owner / Wave iX | Completed
Telephony Integration | 09/05/2024 | Owner / PMO | Completed
Listen Mode Enablement | 11/25 | Wave IX | Completed
Listen Mode Analysis | 12/9 | CS/WaveIX AI | Completed
Intent identification and Automation | TBD | WaveIX AI Agent | In_Progress
Performance Review and Evaluation | TBD | WaveIX/CS/Ops | To-do

## Slide 6
Leslie – WaveIX AI Agent
PROGRESS UPDATE
Scoping Call done with WaveIX team on setting up AMP on Leslie’s Pool by 12/9.
WaveIX team is reviewing and opting the Use cases to be automated for Phase 1.
WaveIX team needs access to the Manhattan Active omni platform, WaveIX team is working with IT POC from client side.
WaveIX is working on the scoping before start integration discussion.
Calls flow diagrams has been shared with WaveIX team for the below cases
          1 .In the pool
        2. Leslie’s
        3.Pool Supply world.
        API architecture diagrams, clarify FAQ format needs to be shared with WaveIX team.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
API documentation needs to be shared with the WaveIX AI agent
Call flow diagram. For Leslie’s pool.
Finalized scope needs to be shared by WaveIX team by 12/16.
Critical Milestones | Due Date | Owner(s) | Status
Demo | 11/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 12/16 | Wave IX | In Progress
Telephony Integration | TBD | Wave IX | To-do
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 7
TiVo – WaveIX AI Agent
PROGRESS UPDATE
API access provisioned for Ibex WaveIX team.
Tech session with TiVO is done on 12/12.. The end points are discussed.
TiVo IVR Flow are shared with WaveIX team.
Working on FAQ’s on engaging the customers.
NEXT STEPS
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
CGC raised a concern of multiple duplicate records in reporting due to call deflection. | Reporting issues | CGC will keep participant ID same and wont change without informing Insight team Insight team will filter our the call legs with said participant ID. |  |  | Resolved
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
WaveIX will test the connectivity on additional URLs and confirm if all goes well we will proceed to the next step.
Need to check with Pavel what covers in MVP for Phone’s LOB’s perspective. Idea is to ensure if we have right access to the API end point to automate the case we need.
Critical Milestones | Due Date | Owner(s) | Status
Demo | 8/20 | Wave IX | Completed
Kick Off | 11/20 | Wave IX | Completed
Discovery | 11/25 | Wave IX | Completed
Telephony Integration | TBD | Wave IX | In Progress
Back-end system integration | TBD | Wave IX | To-do
Testing & Pre Go-:Live | TBD | Operations | To-do
Go-:Live | TBD | Operations | To-do

## Slide 8
Custom Ink – WaveIX AI Agent
PROGRESS UPDATE
A custom demo environment is handed over to CI.
Client will review and share feedback
Working on finalizing SOW
NEXT STEPS
Client feedback awaited.
Sign SOW and share project plan and timeline with Custom Ink
After approval start working on intent automation.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initial Demo to Client | 07/18/2024 | Owner / PMO | Completed
Telephony Integration | - | Owner / PMO | N/A
Listen Mode Enablement | 09/09/2024 | Wave IX Team | Completed
Listen Mode Analysis | 10/08/2024 | Eric | Completed
Performance Review and Evaluation | 11/18 | Client / PMO | In-Progress
Intent identification and Automation | 12/1 | Wave IX Team | In-Progress
SOW Finalization | TBD | Client | To-do

## Slide 9
Conifer – Wave IX Accent Localization
PROGRESS UPDATE
Pilot in Progress
Work performance data and feedback has been shared with Wave IX Accent team.
The problem In hand is that the tool(Krisp) worked well on the Female profile and doesn’t work well for the male profile.
Vendor advised to use a disclaimer script about the voice shaping to avoid questions from the customer about the roboticness of the call.
Vendor acknowledge and working on the fix in next release 12/16.
NEXT STEPS
Pilot to complete EO2024
Vendor acknowledge and working on the fix in next release 12/16..
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Vendor Communication | Jan 2024 | PMO / MT | Completed
Testers Alignment | 09/01/2024 | PMO | Completed
Test Stations Setup | 09/02/2024 | PMO / ITFS | Completed
AL App Deployment | 09/02/2024 | ITFS | Completed
Get approval to implement | 09/02/2024 | CS | Completed
Initiate Pilot | 09/04/2024 | CS / PMO / Wave IX | Completed
Results Analsys | 12/31 | CS / PMO / Wave IX | In-Progress

## Slide 10
UHC – Wave IX Accent Preservation
PROGRESS UPDATE
Client agrees to have Preserve mode deployed on the Production (No Pilot)
Installation on PH (Davao, Bohol) done on around 144 Workstations.
Weekly Monitoring session with Vendor and Ops for the progress.
NPS score and performance started deteriorating.
Krisp to push another improves release.
CS decided to remove preserve from larger population.
Only 10 agents to kept active on Preserve.
As per vendor advice, we are halting the usage of preserve mode on more than 10 inbstances.
Next improved release expected by 12/16
NEXT STEPS
Monitoring the performance.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Demo to the Client | 11/25 | WaveIX/Client | Completed
Client Approval | 11/25 | Client | Completed
Testing (Pilot) | 11/28 | WaveIX | Completed
Deployment | 12/3 | WaveIX | Completed
Monitoring | 12/13 | WaveIX | In-Progress

## Slide 11
Other 3rd Party Tools
3rd Party Partner | Wave iX Solution | Description
Envoy Visitor | Not under Wave iX | Envoy Visitors is a cloud based electronic visitor management system that streamlines the check-in process, enhancing security and visitor experience by digitizing sign-ins and tracking in workplaces.

## Slide 12
Envoy – Electronic Visitor Management Solution
PROGRESS UPDATE
A digital replacement of conventional paper based system.
Initially deployed to 4 ibex sites last year as part of Google VoVo audit.
It was planned to expand to other sites in future as well.
Currently we are using Premium licenses.
Amazon compliance audit also mandated to use EVMS on all amazon sites.
We have reviewed and opted for its Enterprise version due to more security features.
Pricing approval in progress.
Licenses and equipment procured
NEXT STEPS
Site configurations, hardware deployment
Go-Live.
Key Risks – Description | Impact | Resolution Action / Risk Mitigation | New Target Due Date | Owner(s) | Status
Hardware availability in PH and PK | Delay | Needs to be hand carried from US | TBD | PMO / Procurement | Pending
Project Manager | Project Oversight
Sinnan Khan | Ahsan Tirmizi Zeeshan Ahmed
Critical Milestones | Due Date | Owner(s) | Status
Initiate Vendor Communication | March 2024 | PMO / Procurement | Completed
Feature and Pricing Review | April 2024 | PMO / Procurement / Compliance | Completed
Pricing Negotiation | July 2024 | Procurement | Completed
Gather Site and Regional Approvals | August 2024 | PMO | Completed
Gather Management Approval | September 2024 | Procurement | Completed
Place Orders | October 2024 | Procurement | Completed
Deployment | December 2024 | PMO / ITFS | Pending
3rd Party Tools

## Slide 13
Thank you.