## Translate-Plan
Phase | Task | Description | Assignee | Start Date | End Date | Duration (Days) | Status | Risks
Discovery | Meeting with Client | sharing agenda with the client, ptich, demostration | S. Pavel/E. Guerra |  |  |  | Not Started
| Content Discovery | Insight on Call Data, Focus use cases and goal statement for RTT | IT PMO/S. Pavel/E. Guerra/Client POC |  |  |  | Not Started
| Understanding Client's ACD | Discuss and review Cross platform dependencies, Languages required, Amazon Connect, Five9, Avaya etc | IT PMO/S. Pavel/E. Guerra/Client POC |  |  |  | Not Started
Planning | Define project scope and objectives | Collect requirements, Transform requirements into Scope, create WBS, | IT PMO |  |  |  | Not Started | Scope creep if requirements are unclear
| Resource Identification & Allocation from Client & Wave iX Translate Teams, Ops & Testers | allocate project resources across different teams i.e.Wave iX Translate genesys etc | IT PMO |  |  |  | Not Started | Missing key stakeholders
| identify use cases - Call flows | How operations will use and test the feature. | IT PMO |  |  |  | Not Started
| Identify activities and Establish Project Schedule | identify activities, build Activity Network Diagram, Identify Critical pathm identify Durations, Manage Reserves, build Project Schedule. | IT PMO |  |  |  | Not Started
| Publish Ptoject Timelines and Get Sign Off | Publish Ptoject Timelines and Get Sign Off | IT PMO |  |  |  | Not Started | Miscommunication between teams
Tech Discovery | Tech Sessions with Client | Tech workshop with client’s telephony experts.Telephony experts to advise on system integration incl caller validation | Client POC & Wave iX Translate |  |  |  | Not Started
| Client Platform Access Provision | Client Platform Access Provision | IT PMO |  |  |  | Not Started
| Telephony system compatibility | Wave iX will check if SIPs configured and enabled in client's telepohony system. | Wave iX Translate |  |  |  | Not Started
| CCaas Compatibility | Wave iX will check if Client's platform is compatible with Wave iX Translate | Wave iX Translate |  |  |  | Not Started
| API and Telephony Platform Dependencies | Voice Media Codec Support, Audio Quality, API documentation and accessibility | Wave iX Translate |  |  |  | Not Started
| Languages required | Language Support: Verify if the telephony platform and Wave iX Translate support the same languages for voice and text interactions. language model should match the target audience's language. | Wave iX Translate |  |  |  | Not Started
| Customize configuration for client | General configuration of prompts for GPT model, internal testing | Wave iX Translate |  |  |  | Not Started
| Confirmation to the Client | Based on the above discovery activity | S. Pavel/E. Guerra |  |  |  | Not Started
Design | Collect IPs and URL from Wave iX Translate | need to collect IPs, FQDN that needs to be whitelisted on client ACD | IT PMO |  |  |  | Not Started
| Collect IPs and URL from Client ACD platform | need to collect IPs, FQDN that needs to be whitelisted on Wave iX Translate | IT PMO |  |  |  | Not Started
| Validate network requirements | Open the required ports and whitelist IP ranges as specified in both Genesys and Wave iX Translate documentation. | IT PMO |  |  |  | Not Started
| Request For ticket to Whitelist the traffic between two end | Request For ticket to Whitelist the traffic between two ends | IT PMO |  |  |  | Not Started
| Confirm all the information required to configure Translate Engine | In this task, we will gather all the information required to configure translate platform | Client POC/Wave iX Translate |  |  |  | Not Started
Implementation | Creation of DID and Pvt Numbers, orgs | Creation of DID and Pvt Numbers, orgs | Client POC/Wave iX Translate |  |  |  | Not Started
| Set up SIP/PSTN trunk between Wave iX Translate and Client ACD | Set up SIP/PSTN trunk between Wave iX Translate and Client ACD | Client POC/Wave iX Translate |  |  |  | Not Started | Incorrect SIP trunk settings
| Configure SIP trunk in Wave iX Translate | Configure SIP trunk in Wave iX Translate | Wave iX Translate |  |  |  | Not Started | Configuration delays
| Whitelist IPs and APIs, FQDN, URLs for Client ACD | Whitelist IPs and APIs, FQDN, URLs for Client ACD | Wave iX Translate |  |  |  | Not Started
| Whitelist IPs and APIs, FQDN, URLs for Wave iX | Whitelist IPs and APIs, FQDN, URLs for Wave iX | Client POC |  |  |  | Not Started
| Configure Ibex Translate for each requested language | In this phase, Wave iX team will configure translate platform | Wave iX Translate |  |  |  | Not Started
| Wave iX LLM configuration and Optimisation | In this phase, Wave iX team will Optimise the out of the box features | Wave iX Translate |  |  |  | Not Started | Firewall rules blocking communication
Training & Testing | Access provisionings for Ops | need to provide access to the Operations | Wave iX Translate |  |  |  | Not Started
| Train the Trainer | Need to train the trainer | Wave iX Translate |  |  |  | Not Started
| Train the Agents | Train the Agents | Operations Team |  |  |  | Not Started
| Perform test calls from Genesys to Wave iX Translate | 1. test calls. 2. Conduct language-specific testing to evaluate dialog flows, pronunciation accuracy, and customer satisfaction 3. TTS-STT testing | Operations Team |  |  |  | Not Started | Signaling or audio quality issues
| Test call flows and workflows | Test call flows and workflows | Operations Team |  |  |  | Not Started | Workflow misalignment between platforms
| Signoff for Go-Live | Signoff for Go-Live | Operations Team |  |  |  | Not Started | Resolution delays impacting timelines
Deployment | Formal Ticket & Notification, Bridge reservations | Finalize deployment plan, notify client, Ops and teams | IT PMO |  |  |  | Not Started
| Execute deployment | Deployment | Client POC & Wave iX Translate |  |  |  | Not Started | Deployment errors or unexpected downtime
| Post-deployment monitoring activity | Monitoring of calls and project KPIs, gather agent, feedback for improvements | Client POC |  |  |  | Not Started | Latency or connectivity issues post-deployment
Closure | Document lessons learned | Document lessons learned | IT PMO |  |  |  | Not Started | Missing critical feedback
| Handover to operations | Handover to operations | Operations Team |  |  |  | Not Started | Incomplete documentation or training

## stakeholder Register
Role | Name | email | Organization | Roles
Technical Coordination (Client-Side) |  |  | Modivcare | A technical representative from the client is required to coordinate technical aspects.
Business Coordination (Client-Side |  |  | Modivcare | A business representative from the client is needed for discussions. Typically, Pavel, Eric, and Zeeshan will handle this.
Parloa Representatives – |  |  | Parloa | a one who desgins the BOT i.e.
Design Escalation (Partner-Side) |  |  | Parloa | A designated person from the partner side will handle design escalations.
BOT Technical Support |  |  | Parloa | A resource is needed for API and routing-related BOT design.
Technical Escalation (Partner-Side) |  |  | Parloa | A technical representative from the partner side will handle escalations.
Level 2 Escalation -(Partner Side) |  |  | Parloa | This role is necessary for Level 2 escalation handling.
Client Services (Ibex | Boyd Blanton | Blanton, Boyd <Boyd.Blanton@ibex.co> | Ibex | A representative from Ibex client services will assist.
Operations Support – OM | TBD |  | Ibex | Someone from operations will help in gathering details on use cases.
Training Support | TBD |  | Ibex | Training Support – The training team will assist with FAQs and other operational tasks.
Technical Coordinator - (ibex Side) | Wasiq Ashfaq | wasiq.ashfaq@ibex.co | Ibex | Ibex side technical coordinator
Implementation Manager | Sinnan Khan | Khan, Sinnan <Sinnan.Khan@ibex.co> | Ibex | IT Implementation Lead – A person responsible for IT implementation.
Wave iX | Pavel Sardar | Sardar, Pavel <Pavel.Sardar@ibex.co> | Ibex | Project Manager – A designated project manager will oversee the implementation.
Wave iX | Eric Guarra | Guarro, Eric <eric.guarro@ibex.co> | Ibex | Overall Wave iX Lead – The lead for Wave iX will be involved.
IT Implementation - Escalation | Zeeshan A | Ahmed, Zeeshan <Zeeshan.Ahmed@ibex.co> | Ibex | IT Implementation Escalation – A resource will be needed for IT-side escalations.
IT Implementation - Oversight | Ahsan Tirmizi | Tirmizi, Ahsan <ahsan.tirmizi@ibex.co> | Ibex | Implementation Oversight – Responsible for overseeing the overall implementation.

## Usecase
Usecase | area | steps to execute | Phase | Status
use case 1 …........... |  | Step 1 : customer dial TFN etc… Step 2 : IVR etc… | 1
use case 2 …........... |  | Step 1 : customer dial TFN etc… Step 2 : IVR etc… Step 3: Activate Sim | 1
use case 3 …........... |  | Step 1 : customer dial TFN etc… Step 2 : IVR etc… Step 3 : ….. Translate | 1
use case 4 …...........
use case 1 …........... |  | Step 1 : customer dial TFN etc… Step 2 : IVR etc… | 2
use case 2 …........... |  | Step 1 : customer dial TFN etc… Step 2 : IVR etc… Step 3: Activate Sim | 2
use case 3 …........... |  | Step 1 : customer dial TFN etc… Step 2 : IVR etc… Step 3 : ….. Translate | 2
use case 4 …...........