## Sheet1
Activities | Owner | End Date(ETA) | Status | Action items
Development Instance readiness
Dev API provisioning | Ibex | 2025-03-05 | Done
RTT Dev Instance Provisioning | Partner | 2025-03-14 | Done
Payment Processing work | Ibex | 2025-03-21 | Done
Testing | Ibex | 2025-03-24 | Done | Ongoing Issue: call is not being appeared on Ibex Translate
confirmation | Ibex | 2025-03-24 | Done
Production Instance readiness
Prouction API provisioning | Ibex | 2025-03-20 | Done | Ahsan to connect with Ibex team for this
RTT Prod Provisioning and integration prod APIs | Partner | 2025-03-26 | In-Progress | Partner to provide, AOC discussion is pending.
Deploy and test | Ibex | 2025-03-27 | Done
Ccaas>< WaveiX changes
Discuss Trunk changes with client i.e. creation of Queues that will | RRI/Wave IX | 2025-03-19 | Done | discussed with client
Approval from client for Test environment changes | RRI | 2025-03-20 | Done | Approved with Shanna for Test Env
Implement change | RRI | 2025-03-25 | Done | done, waiting for the confirmation on the queue assignment
Testing E2E - Lab | Wave IX | 2025-03-26 | In-Progress | Partner, Ibex are working on it
Approval from client for Prod environment changes |  | 2025-03-27 | To-do | We can request tonight with client
Implement change in Prod | RRI | 2025-03-27 | To-do
Testing E2E - Prod | Wave IX | 2025-03-27 | To-do | Final E2E
Go live
Go live |  | 2025-04-01 | to-do
Monitoring |  | 2025-04-02 | to-do