## Project Plan
Task(s) & Milestones | Desctiption | Assignee | Start Date | End Date | Duration | Status | Comment
1. Intro Call (1 Week)
a. Intro call with Wave iX team (internal call) | i.e. all participants partner, PMO, Pavel & Eric. | Wave iX Team |  |  |  | Done
b. Intro call with client - Kick off and POC identification | i.e. what value we are delivering with the proposed solution. | Wave iX Team,Client |  |  |  | In-Progress | need to ask the roles and POC from Wave iX and generate the
2. Discovery Workshop (1 Week)
a. Identify Stakeholders | i.e. Roles and Responsibilities from Client and Wave iX end. | Wave iX Team | 2025-01-06 | 2025-01-13 | 7 | In-Progress
b. Gather Operational Requirements and usecase identification for automation | i.e. Document client’s IVR, FAQs, operational workflows and gather other supporting materials and documentation from Client services or Operations | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 | 7 | In-Progress | need to connect with pavel on the usecase inclusiion. Ahsan to setup 1/28
c. Identify Key Operational Pain Points | i.e. Highlight areas for improvement | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 | 7 | In-Progress | need to double check with pavel & Alfy
d. Identify and Establish KPI(s) and their current and forecasted value. | Meet up with the CS and Operations and gather list of KPIs measuring the success criteria | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 | 7 | In-Progress | need to be checked with Pavel
e. Compliance/Security Review (if required) | Ensure solution design meets data privacy, security, and compliance standards. | Wave iX Team, Security | 2025-01-06 | 2025-01-13 | 7 | Done
3. Tech Discovery (1 Week)
a. Tech sessions for understanding client platform (if required) | e.g. CCaas? CRM? KB? - This information may be available during sales process. | Wave iX Team/Client | 2025-01-13 | 2025-01-24 | 11 | Done
b. Assessment of the platform and see if we need to develop customizations for the enablement. | Wave iX team will check if we have out of the box integration solution or do we need to develop customize code | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | Done
c. Collect URLs VoIP/Https from both end to whitelist | For establishing the Secure communication whitelisting from both ends needs to be done. Genesys & wave IX , Wave IX and CRM | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | In-Progress | we have access to the dev or staging salesforce. We need to get for the production as well
h. Tech session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client. | Conduct a session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client and discuss the API details | Wave iX Team/Client | 2025-01-13 | 2025-01-24 | 11 | Done
g. Get API Access from source CCaaS, CRM, KB i.e. User Creation | Access provision from the on the CCaaS, CRM, KBs. | Client | 2025-01-13 | 2025-01-24 | 11 | In-Progress | we have access to the dev or staging salesforce. We need to get for the production as well
f. Review API Documentation and prepare questions | documentation of CRMs, ACDs etc | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | In-Progress | needs to be reviewed with Wasiq 1/28. follow up
e. System Architectural Diagram | i.e. diagram to visually analyze the configuration scenario | Wave iX Team/Ops | 2025-01-13 | 2025-01-24 | 11 | Done
d. Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | Done
e. Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | Done
4. Listen Mode Enablement(3weeks) (if required)
a. Assess Telephony Requirements | i.e. DID creation, Call Forwarding | Wave iX Team |  |  |  | Done
b. Plan Telephony Integration | i.e. raise formal tickets or request | Wave iX Team |  |  |  | Done
c. Implement Telephony Integration | Implement Telephony Integration | Wave iX Team |  |  |  | In-Progress
d. Integration Testing | i.e. make Test Calls E2E and monitor logs, take Go-No Go | Wave iX Team |  |  |  | To-Do
e. Enablement of Listening Mode | Enablement of Listening Mode | Wave iX Team |  |  |  |  | Not required
5. Listen Mode Data Analysis
Collect Data and build Analytics |  | BI |  |  |  | To-Do
Use case identification, |  | BI |  |  |  | To-Do
Draw Flows, understanding Flows |  | BI |  |  |  | To-Do
5. Scoping(1 Week)
a. Tech sessions with Client POC on Analytics on Listen Mode. | showcase them possession of the calls traffic | Wave iX Team/Client |  |  |  | Done
c. Scoping Call with Client i.e. What needs to be delivered in Subsequent Phases | i.e. Phase 1 Flow 1, Flow2, Flow 3 .Phase 2 Flow 4, Flow 5, Flow 6. | Wave iX Team/Client | 2025-01-13 | 2025-01-17 | 4 | Done
d. Identify Call routing Flows and detailed Usecase steps from Operations | need detailed step by step of each flow right from the call receiving and involving steps in the CRM | Wave iX Team/Operations | 2025-01-13 | 2025-01-17 | 4 | Done
d. Identify FAQs | need to collect and en-scope FAQ(s) that needs to be automated by IVR Bot. It can be available on pubic forum or Operations can guide us |  | 2025-01-27 | 2025-01-31 | 4 | To-do | TiVo's FAQ are available on the public forum, we can advise Development team to pull the data from the public forums via Web Scrapping
d. Initiate Tech Session with Client on Mapping Usecases with APIs | Initiate Tech Session with Client on Mapping Usecases with APIs | Wave iX Team/Operations | 2025-01-27 | 2025-01-31 | 4 | To-do
e. Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Wave iX Team/Client | 2025-01-27 | 2025-01-31 | 4 | To-do
f. Develop Formal Scoping Document and Signoff | Formal Scoping Document and Signoff | Wave iX Team/Client | 2025-01-27 | 2025-01-31 |  | Done
6. Integration in Telephony i.e. SIP or PSTN (2 Weeks) |  | Wave iX Team | 2025-01-27 | 2025-01-31
a. Assess Telephony Requirements |  | Wave iX Team | 2025-01-27 | 2025-01-31 |  | Done | need to check if we can remove the earlier block for our TiVo client since we don’t need Listening mode
b. Plan Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 |  | Done
c. Implement Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 | 4 | To-Do
D. Test Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 | 4 | To-Do
7. BOT Designing |  | Wave iX Team |  |  |  | To-Do
7.1 Setup BOT Persona |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Define Role | helps you define the purpose and context of the AI Agent. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define Tone | tab enables you to define the communication style of the AI Agent | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
c. Instruct BOT | tab provides specific operational guidelines that the AI Agent should follow during its interactions | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.2 Setup Phone | Set up everything required to create a great experience for customers interacting with your AI Agent over the phone | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Define Voice & Language |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define Ambient Sound |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
c. Define End of Speech Recognition Sound |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
d. Define AI Agent is Thinking Sounds |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
e. Define Fine Tunings |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.3 Setup Routing Skill(s) |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Identify client specific routing Skills (destinations) in the IVR i.e. Sales Representative, Activation Options | Need to add client specific routing Skills (destinations) in the IVR i.e. Sales Representative, Activation Options. It depend on the scope and elaborated use cases flows. We need to Add routing skills separately | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define Routing Skill(s) | define the Routing Skill i.e. instructing BOT when to use that particular route, also explicitly mention the parameters which facilitate BOT to deliver to the destination i.e. call summary, customer name, call id, caller number etc | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
1. Define Route i.e. SIP URI with routing Endpoint |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
1. Define instruction to BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
3. Fall back Messages |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
3. Deine Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.4 Setup Knowledge Skill |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Define and Emphasize Source-Only Retrieval |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Filter Questions to Resolve Ambiguities |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
c. Agent Role and Company Context |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
d. Consistent Prompt Framework |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
e. Source Formatting |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
f. Logical Grouping of Sources in Collections |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
g. Content Length |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
h. Adapt Content for Telephony |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.5 Setup Custom Skill(s) | The Custom Skill enables AI agents to interact with third-party systems using APIs. This allows AI agents to retrieve and send data to external systems, perform actions such as updating records or initiating transactions, and provide users with a seamless experience by integrating various backend systems into a single conversational interface | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7. 6 Simulations & Prompt Engineering |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do
a. Define LLM Params |  | Wave iX Team | 2025-02-03 | 2025-02-11 |  | To-Do
c. CX Design: Set up simulations and evaluations |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | Keep it for now, will see it later
d. CX Design: AMP Prompt Engineering |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | Keep it for now, will see it later
8. Integration Backend System (2 Weeks) | i.e. Wave iX services Integration with CCaaS's and CRM's APIs. |  | 2025-02-03 | 2025-02-11 |  | To-Do
a. Implementation of Use Cases in Wave iX and Integration Feedback | Implementation of Use Cases in Wave iX and Integration Feedback | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do
9. QA & QC |  | Wave iX Team |  |  |  | To-Do
a. Develop Test case for Testing AI BOT |  | Wave iX Team | 2025-02-12 | 2025-02-19 |  | To-Do
a. BOT Testing |  | Wave iX Team | 2025-02-12 | 2025-02-19 |  | To-Do
c. Define Centralized Space for Reporitng and sharing Bugs |  | Wave iX Team | 2025-02-12 | 2025-02-19 | 7 | To-Do
d. Bug Fixing & Regression Testing |  | Wave iX Team | 2025-02-12 | 2025-02-19 |  | To-Do
e. Go-No Go. Sign Off | Go-No Go. Sign Off | Wave iX Team | 2025-02-12 | 2025-02-19 | 7 | To-Do
9. User Acceptance Testing & Optimization |  | Wave iX Team |  |  |  | To-Do
a. Identification of Test Case with the help of CS & Ops. | Ops will come up with the pre-defined test cases | Ops | 2025-01-20 | 2025-01-24 | 4 | To-Do
b. Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Wave iX Team | 2025-02-17 | 2025-02-21 | 4 | To-Do
b. Schedule and Conduct Session for testing on Official Bridges. | Schedule and Conduct Session for testing on Official Bridges. | Wave iX Team | 2025-02-17 | 2025-02-19 | 2 | To-Do
c. Review Results with Wave iX Team | Review Results with Wave iX Team and see if we need to develop | Wave iX Team | 2025-01-20 | 2025-01-20 | 0 | To-Do
Go-No Go Sign Off from Project Team |  |  | 2025-01-20 | 2025-01-20 | 0 | To-Do
10. Go-Live | [5 empty] | To-Do
a. Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
b. Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
c. Bridge Reservation and Go-Live | Bridge Reservation and Go-Live | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
d. Go-Live |  | Wave iX Team | 2025-02-24 | 2025-02-24 |  | To-Do
e. Monitoring bridge | Monitoring bridge | Wave iX Team | 2025-02-24 | 2025-02-28 |  | To-Do
11. Ongoing Testing and Review of Conversations in AMP | [5 empty] | To-Do
a. Adaptation | retrospective | Wave iX Team | 2025-03-03 | 2025-03-05 |  | To-Do
b. Refinements | Refinements | Wave iX Team | 2025-03-06 | 2025-03-07 |  | To-Do

## IVR Flow
LOB Name | Main Menu | Sub menu | Action | End Point | Genesys Queue Name | Queue Type | Hoops Weekdays | HOOPS Weekends | Hoops Weekdays | HOOPS Weekends
TiVo - TFN Buy TiVo With Chat Option +1 877-916-2888 +1 877-916-4888 +1 877-917-5888 +1 877-920-2555 +1 877-920-7111 +1 877-921-6555 +1 877-921-8555 +1 888-280-3219 +1 888-386-1071 +1 888-393-1148 +1 888-402-6195 +1 888-420-3189 +1 888-488-0143 +1 888-488-0144 +1 888-488-0149 +1 888-488-0150 +1 888-577-1058 +1 888-596-9852 +1 888-663-6214 +1 888-663-6216 +1 888-679-2806 +1 888-679-2807 +1 888-771-7793 | Thanks for calling Tivo customer support. This call will be recorded for quality and record-keeping purposes. If you want to make changes to your account, activate a device, or update your credit card, please visit us at tavo.com forward slash my account. If you are experiencing a technical issue, please visit us at tavo.com forward slash support for troubleshooting help.
| Press 5 If you are calling from a mobile phone and would like to save time by accepting a text message from Tivo that will connect you with our virtual assistant |  | Transfer to Number: 471954
| Press 1 for new customer to add TiVo device to account |  | Transfer to Flow: Sales Fulfillment - Sub flow | Route to Agent | Tivo Sales Fullfillment-2917
| Press 2 for new customer to purchase TiVo Device |  | Transfer to Queue: TiVo New Cust Sales-2917 | Route to Agent | TiVo Customer Service-2917
| Press 3 for everything else |  | Transfer to Flow: TiVo - Customer Service- Sub flow |  | TiVo Customer Service-2917
| Press 5 to receive a text message to connect to virtual assistant |  | Transfer to Number: 471954 (IVR for chat)
LOB Name | Main Menu | Sub menu | Action | End Point | Genesys Queue Name | Queue Type | Hoops Weekdays | HOOPS Weekends | Hoops Weekdays | HOOPS Weekends
TiVo - TFN Buy TiVo without Chat Option | Press 1 for new customer to add TiVo device to account |  | Transfer to Flow: Sales Fulfillment - Sub flow | Route to Agent | Tivo Sales Fullfillment-2917
| Press 2 for new customer to purchase TiVo Device |  | Transfer to Queue: TiVo New Cust Sales-2917 | Route to Agent | TiVo Customer Service-2917
| Press 3 for everything else |  | Transfer to Flow: TiVo - Customer Service- Sub flow | Route to Agent | TiVo Customer Service-2917
LOB Name | Main Menu | Sub menu | Action | End Point | Genesys Queue Name | Queue Type | Hoops Weekdays | HOOPS Weekends | Hoops Weekdays | HOOPS Weekends
TiVo - TFN for TiVo - Without Chat Option | Thanks for calling TiVo customer support. Please choose from the following four options
| Press 1 for technical support | Tech Support subflow One of our technical support representatives will be with you shortly. You can also chat with us online or send your questions via email. Visit tivo.com forward slash support to take advantage of these time-saving options or to speak with a representative, please choose from the following four options.
|  | Press 1 For hookup, setup and networking | Transfer to Queue: TiVo Networking-2918 | Route to Agent | TiVo Networking-2918
|  | Pres 2 For help with cable cards | Transfer to Queue: TiVo Cable Card-2918 | Route to Agent | TiVo Cable Card-2918
|  | Press 3 To report missing or incorrect program guide information, such as missing channels or incorrect program descriptions | Transfer to Queue: TiVo Line Up Card-2918 | Route to Agent | TiVo Line Up Card-2918
|  | Press 4 For everything else | Transfer to Queue: TiVo TechSupport-2801 | Route to Agent | TiVo TechSupport-2801
| Press 2 for Billing and account related questions | Billing Account Menu To make quick, easy changes to your account and billing information, including updating your credit card, please visit tvo.com forward slash my account. To speak with the representative, please choose from one of the following three options.
|  | Press 1 To update your credit card. | Transfer to Queue: TiVo Credit Card Update-2917 | Route to Agent | TiVo Credit Card Update-2917
|  | Press 2 to cancel your Tivo service | Transfer to Queue: TiVo Retention-2917 | Route to Agent | TiVo Retention-2917
|  | Press 3 For all other questions | Transfer to flow: Tivo - Customer Service |  | TiVo Customer Service-2917
| Press 3 to activate service on a tivo box |  | Transfer to Flow: TiVo - Activation - Sub flow | Route to Agent | TiVo Activations-2917
| Press 4 to purchase tivo products |  | Transfer to Flow: TiVo - Sales Fulfillment- Sub flow | Route to Agent | Tivo Sales Fullfillment-2917
LOB Name | Main Menu | Sub menu | Action | End Point | Genesys Queue Name | Queue Type | Hoops Weekdays | HOOPS Weekends | Hoops Weekdays | HOOPS Weekends
TiVo - TFN for TiVo With Chat Option +1 877-367-8486 +1 877-777-9017 +1 877-851-8997 | Thanks for calling Tivo customer support. This call will be recorded for quality and record-keeping purposes. If you want to activate a device or update account and payment information, please visit us at tivo.com forward slash my account. If you are experiencing a technical issue, get help at tivo.com forward slash support for troubleshooting help.
| If you are calling from a mobile phone and would like support via text message from Tivo, press 5 |  | Transfer to number: 47195
| Press 1 for Billing and account related questions | Billing Account Menu To make quick, easy changes to your account and billing information, including updating your credit card, please visit tvo.com forward slash my account. To speak with the representative, please choose from one of the following three options.
|  | Press 1 To update your credit card. | Transfer to Queue: TiVo Credit Card Update-2917 | Route to Agent | TiVo Credit Card Update-2917
|  | Press 2 to cancel your Tivo service | Transfer to Queue: TiVo Retention-2917 | Route to Agent | TiVo Retention-2917
|  | Press 3 For all other questions | Transfer to flow: Tivo - Customer Service |  | TiVo Customer Service-2917
| Press 2 to Activate service on a Tivo device |  | Transfer to Flow: TiVo - Activation - Sub flow | Route to Agent | TiVo Activations-2917
| Press 3 to purchase a Tivo device |  | Transfer to Flow: TiVo - Sales Fulfillment- Sub flow | Route to Agent | Tivo Sales Fullfillment-2917
| Press 4 for Technical support for Romeo, Bolt, Edge and Tivo Stream 4k | Tech Support subflow One of our technical support representatives will be with you shortly. You can also chat with us online or send your questions via email. Visit tivo.com forward slash support to take advantage of these time-saving options or to speak with a representative, please choose from the following four options.
|  | Press 1 For hookup, setup and networking | Transfer to Queue: TiVo Networking-2918 | Route to Agent | TiVo Networking-2918
|  | Pres 2 For help with cable cards | Transfer to Queue: TiVo Cable Card-2918 | Route to Agent | TiVo Cable Card-2918
|  | Press 3 To report missing or incorrect program guide information, such as missing channels or incorrect program descriptions | Transfer to Queue: TiVo Line Up Card-2918 | Route to Agent | TiVo Line Up Card-2918
|  | Press 4 For everything else | Transfer to Queue: TiVo TechSupport-2801 | Route to Agent | TiVo TechSupport-2801
Note that technical support for devices older than Romeo is available at tavo.com forward slash support.

## New User Activation (DVR&Mini)
Opening: "Thank you for calling TiVo. My name is _____. May I have your name please?"
Account Lookup:
Check if it is a new customer:
1. Select Accounts on the drop-down menu located on the upper left portion in Service Console.
2. Click New. Select Person Account then click Next.
3. Fill-out the customer information
Existing customer and account auto-populate.
1. Verify the email address.
2. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Existing customer and account is not auto-populate.
1. Get the caller’s name and phone number to search for the account.
2. Once the account is found, verify the email address.
3. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Activation pre-requisite:
• Verify if the device(s) to activate is a Series 5, 6, 7, VOX or a TiVo Mini as we do not activate service for Series 1 - Series 4.
• Use Global Search and the scenarios below to verify if the TSN is free to activate;
|  | If the device is activated with Monthly and Annual service | • Refer the new customer to the previous owner to request service cancellation to proceed with activation
• If no contact with the previous owner, see How to Transfer Ownership - (Monthly/Annual) and Exception Process
|  | If the device is activated with All-In Plan service | • Do not process activation. See How to Transfer Ownership: All-In Plan and PLS
|  | If the device is received with a Service Transfer Letter | • Do not process activation
• Check previous case(s) if customer receive a save offer. Consult L2, if necessary
• Check order section to verify if the device(s) is purchase with Service Transfer Letter.
Note: L3/ ESL approval is required if device with Service Transfer Letter is purchased for AIP transfer. To know more, see How to Transfer TiVo Service to a New TiVo DVR
|  | If the device is purchased from Weakness and NCTC | • Do not process an activation
• See How to Transfer Ownership: WeaKnees Account
• See How to Transfer Ownership: NCTC Account
|  | If the device is received as a replacement from a 3rd party retailer | Scenario 1: The customer receive the same device model (within 30-day or beyond 30-day from purchase date).
• Do not process activation
• Ask the customer to send a proof of exchange
• Send it to TiVoACS@xperi.com with the subject line Attn to TiVo Case Number ########
• Dial L2 for the next step
Scenario 2: The customer receive a different device (within 30-day or beyond 30-day from purchase date).
• Do not process activation
• Ask the customer to send a proof of exchange
• Send it to TiVoACS@xperi.com with the subject line Attn to TiVo Case Number ########
• Dial L2 for the next step
|  | If the device is received as a replacement from TiVo | • Do not process an activation, check if there is an existing KOT
• Consult L2 if needed
Steps to activate a service:
1. Create a CARE case, click Next.
2. Enter a subject line and save the case.
3. Use Generic TSN to proceed.
4. Use CARE: Standard Care Template and document the request.
5. Choose Activation from the TiVo eCommerce Transactions drop-down.
6. Enter the TiVo Service Number of the device, click continue.
7. Choose a Plan. Click Show Details for more information about the Plan.
Reminder: Before you read the TiVo Service Agreement to the customer. You must read the Limited Warranty mandatory verbiage and make sure the customer agrees. Otherwise, the activation should not push through.
8. Read the TiVo Service Agreement to the customer.
9. If the customer agrees to the terms, click the box to put a check mark on “Yes, customer accepts terms”. Click Next to continue.
10. Ask for the customer's credit card information on the Select Payment Method screen.
Note: When collecting the customer’s information, restate all details to ensure accuracy for the credit card information. Also, TiVo only accepts US based non-prepaid credit cards.
11. Put a check mark on I understand and agree to Agent Store Terms and Conditions, click Finish Activation.
12. Copy and paste the confirmation message on your case notes.
13. Inform the customer that an email confirmation will be received as a reference.
14. Explain to the customer that DVR activation can take between 15 minutes to one hour, advise the customer to wait 15 minutes and then connect to the TiVo service.
Note: TiVo Mini activation can take between 15 minutes to one hour to load the correct software groups to be able to connect to the host DVR. Advise the customer to wait and then run the guided set-up to connect to the host DVR. If still not working, advise the customer to perform the following steps:
a. Force a connection to the TiVo service twice.
b. Power cycle the device.
c. Force another connection.
15. Send an email to the customer linking the setup instructions of the TiVo device along with the case number and self-service option for reference.
Closing the activate case:
1. Click the drop-down menu beside Send an Email option, select Close Transaction Case.
2. Choose the appropriate disposition. Choose the appropriate reason in each field. See sample below:
• Closed > Resolved (Activation) > Prefer Phone Support
3. Categorize the case correctly.
• Activation > New Activation
4. Click to Save.

## New User Activation (Stream 4K)
Opening: "Thank you for calling TiVo. My name is _____. May I have your name please?"
Account Lookup:
Check if it is a new customer:
1. Select Accounts on the drop-down menu located on the upper left portion in Service Console.
2. Click New. Select Person Account then click Next.
3. Fill-out the customer information
Existing customer and account auto-populate.
1. Verify the email address.
2. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Existing customer and account is not auto-populate.
1. Get the caller’s name and phone number to search for the account.
2. Once the account is found, verify the email address.
3. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Note: Prior to activation, make sure the customer has access to a computer, laptop or mobile phone as they will need to enter the activation code using a web browser.
To activate a TiVo Stream 4K:
1. Make sure to Install TiVo Stream 4K.
2. After installation, proceed to Set up TiVo Stream 4K.
3. After completing the initial set up, the activation screen is displayed, ask the customer to use a computer/laptop or mobile phone and go to tivo.com/activate/stream4k to activate the device.
4. On the activation website, the customer must perform the following to proceed:
a. Enter the activation code from the TiVo Stream 4K.
b. Enter the CAPTCHA security verification code. Note: If the CAPTCHA code is unclear, select Reload captcha to generate a new code.
c. Place a check in the checkbox to agree to the User Agreement and Privacy Policy.
d. Select Activate Device to continue to the next page.
Note: The activation code expires after 10 minutes. If the customer is having trouble in activating the device, follow Trouble Activating or Reactivating Your TiVo Stream 4K. If the customer does not agree to the User Agreement and Privacy Policy, they will not be able to proceed with activation.
5. The customer will be asked to create a TiVo account or log in if they have an existing account.
6. Ask the customer to log in or create a TiVo account to complete the activation.
Note: These options will also appear under My Account in Manage My Account should they choose to do this at a later time.
8. Advise the customer to proceed with Personalizing TiVo Stream 4K to complete the set up.
9. Inform the customer that a case number will be sent via email along with the self-service option for reference.
10. Close the case with proper disposition and categorization.

## BIlling Management (Credit)
Opening: "Thank you for calling TiVo. My name is _____. May I have your name please?"
Account Lookup:
Account auto-populate.
1. Verify the email address.
2. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Account is not auto-populate.
1. Get the caller’s name and phone number to search for the account.
2. Once the account is found, verify the email address.
3. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Requisite before giving the information about the status of the credit, verify the following:
1. Check the Credit Card on file, if it is updated. Update the credit card if necessary.
2. Check all accounts for pending settlements, past due or pending credits.
3. Check the TSN returned status (for RFC and for RMA) using FedEx website.
4. Check if it’s within or outside 30-day MBG (for RFC).
Checking the status:
1. Create a CARE case, click Next.
2. Enter a subject line and save the case.
3. Use CARE: General Care case temple.
4. Determine the type of credit.
a. Return for Credit (RFC)
1. Check Store Order status to determine what item(s) the customer purchased.
2. Use Inquiry/Edit on eCommerce drop-down to confirm that the item has been received into our system. (For a Desktop Plus License Key, continue to Step 3.)
Pending Receipt: Verify that the customer has returned the equipment. To verify;
a. Go to Order section and check the RFC Order Status, or
b. Use the FedEx Return Tracking Number to confirm the receipt of the return item(s).
Received: Continue to Step 3.
3. What was returned?
DVR/Mini: Continue to Step 4.
Accessory: Check Braintree to determine whether a credit was issued and transmitted. If no credit has been issued, complete the Problem with a Credit template in your case notes. Then escalate the case to the ACS queue.
Desktop Plus License Key/Gift Card bundle: Consult L2
4. Check the status of the credit in Billing History.
Settled: Inform the customer that the credit has been issued. Depending on the credit card company's billing cycle, the credit may appear on the next billing statement.
Pending Equipment Return: Make sure Step 2 is perform, escalate the case to the ACS queue. Explain to the customer that the credit will settle within 10 business days.
Pending Authorization or Pending Settlement:
• Under 10 days: Advise the customer that it can take within 10 business days to process a credit request.
• Over 10 days: Complete the Problem with a Credit standard text in your case notes. Then escalate the case to the ACS team.
Rejected: Read the case notes regarding why the case was rejected and explain the reason to the customer. If no reason was given, complete the Problem with a Credit template in your case notes. Escalate the case to the ACS queue.
No Credit Memo/Applied Credit:
• Less than 30 days from activation:
• Verify if RFC has been process.
None, follow the normal RFC process.
Yes, escalate the case to the ACS queue.
• More than 30 days from activation:
1. Verify if RFC has been process.
2. Extended MBG has been granted.
3. Follow the normal RFC process. See How to Process a Return for Credit (RFC).
Note: If it has been over 2 business days since the item was received at our shipping center and no refund has been issued, escalate the case to ACS to investigate. Inform the customer to allow for 3-5 days to release the credit and then it could take up to 10 business days for the money to be in their account.
b. Advance Deposit (RMA)
1. Check Store Order to obtain the RMA information.
2. Use Inquiry/Edit on eCommerce drop-down to confirm that the item has been received into our system.
Pending Receipt: Use the FedEx Return Tracking Number to check the status of the return item(s).
• In Transit (within 10 business days): Inform the customer that the item is still in transit to our warehouse. It can take within 10 business days from receipt of the item for a credit to be processed.
• In Transit (over 10 business days): Include the following on your case notes; TSN returned, Return Tracking Number used then escalate the case to the ACS queue on High priority.
Received at Warehouse: Check Braintree to determine whether a credit has been issued.
• Credit has been issued: Inform the customer that the credit has been issued. Depending on the credit card company's billing cycle, the credit may appear on the next billing statement. "Your credit will be issued within 10 business days of TiVo receiving your returned equipment. Depending on your credit card billing cycle, your credit may appear on your next billing statement.”
• Credit has not been issued: Continue to Step 3.
3. When were the items received?
• Less than 10 days ago: Inform the customer that it can take within 10 business days from receipt for the credit to be issued. "Your credit will be issued within 10 business days of TiVo receiving your returned equipment. Depending on your credit card billing cycle, your credit may appear on your next billing statement.”
• More than 10 days ago: Complete the Problem with a Credit template in your case notes. Then escalate the case to the ACS queue with High priority.
Note: If it has been over 2 business days since the item was received at our shipping center and no refund has been issued, escalate the case to ACS to investigate. Inform the customer to allow for 3-5 days to release the credit and then it could take up to 10 business days for the money to be in their account.
c. Bounce Back Order: Undelivered or Refused by Customer
To check the status of a credit, check Order History to verify that the item was received by our shipping center.
1. Open TiVo Store Order . Click the order link.
2. Click the tracking number for the item(s). The FedEx website will appear with tracking information.
3. Read the tracking information to determine the status of the delivery.
Status: Order delivered but refused by customer
• Inform the customer that the device is In Transit to our warehouse and credit will be processed within 10 business days once item(s) is received.
• Process RFC for the order. See How to Process a Return for Credit (RFC).
Status: Order delivered but customer claimed not received
• If the customer insists that they did not receive the order, see TiVo Store Orders: Lost or Missing Items.
Status: Delivery undelivered - In transit (within 10 business days)
• Inform the customer that the item is still in transit to our warehouse.
• Process the Return for Credit and educate the customer that it can take within 10 business days from receipt of the item for a credit to be processed.
Status: Delivery undelivered - In transit (over 10 business days)
• Verify status of the order using FedEx website.
• If there is no movement on the delivery the order may have been lost. See TiVo Store Orders: Lost or Missing Items.
Status: Delivery refused or undelivered - Received at shipping center
• Process a Return for Credit (RFC).
• Inform the customer that it can take within 10 business days from receipt of the item for a credit to be released.
• Escalate the case to ACS queue to check RMA exception report.
4. Check Braintree to see if the credit has been issued. If not, continue to Step 5.
5. If it has been over 2 business days since the item was received at our shipping center and no refund has been issued, escalate the case to ACS to investigate and get the credit released. Inform the customer to allow for 3-5 days to release the credit and then it could take up to 10 business days for the money to be in their account.
d. Manual Credit
1. Check if customer has multiple devices and verify which contract the credit(s) is issued.
2. Verify if credit card is up-to-date. Update the card if necessary.
3. Check the status of the credit in Billing History.
Settled:
1. Check the date when the credit has been settled.
2. Verify with Braintree if the credit was successfully posted.
3. Inform the customer that the credit has been issued. Depending on the credit card company's billing cycle, the credit may appear on the next billing statement.
Suggested Scripting:
"Your credit will settle within 10 business days. Depending on your credit card billing cycle, your credit may appear on your next billing statement."
Pending Authorization / Pending Settlement:
1. Inform the customer that the credit has been issued and verify the last 4-digit of the card.
2. Explain that the credit will settle within 10 business days depending on the credit card company's billing cycle, the credit may appear on the next billing statement.
Suggested Scripting:
"Your credit will settle within 10 business days. Depending on your credit card billing cycle, your credit may appear on your next billing statement."
Rejected:
Read the case notes why the case was rejected and explain the reason to the customer.
If no reason was given, escalate the case to the ACS queue.
5. Categorize and dispose the case accordingly.
6. Send an email to the customer with the case number and the self service option for reference.

## BIlling Management (TOO)
Opening: "Thank you for calling TiVo. My name is _____. May I have your name please?"
Account Lookup:
Account auto-populate.
1. Verify the email address.
2. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Account is not auto-populate.
1. Get the caller’s name and phone number to search for the account.
2. Once the account is found, verify the email address.
3. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Reminder:
You may transfer ownership of ANY model TiVo device with Product Lifetime Service or the All-in Plan. This includes TiVo Premiere Series, TiVo Roamio Series, TiVo BOLT Series, TiVo EDGE Series and TiVo Mini Series.
Process of transferring ownership:
1. Identify the Service State of the device.
Service State 5 (Lifetime Service). Go to Step 2.
Service State 4 (Testing) and Service State 11 (Evaluation/Free Temporary TiVo Service). See Service States 4 and 11 (Lifetime/AIP/Evaluation/Free Temporary TiVo Service)
2. Identify the caller.
a. Current Owner
1. Create a Care case. Use CARE: Ownership Transfer Request case template.
2. Fill out the template accordingly. Include the reason for the request (Example: to give as a gift, sell online or sold to someone) on the Request Summary field.
3. Advise the current owner to do the following to protect their personal information before they give away or ship their TiVo device:
• Unlink all accounts (such as Pandora, Netflix). Send all necessary article on how to unlink accounts.
• Remove anything attached to the TiVo device (such as CableCARDs, DVR expanders, etc.)
• Perform Clear & Delete Everything.
4. Inform that the case number will be emailed. Give the case number to the new owner as a reference for the ownership transfer.
Note: If the current owner is moving devices to one of their accounts, verify the other account and process the request.
b. New Owner
1. Pull-up the new owner’s account. If no account found, assist to create an account.
2. Create a Care case on the new owner’s account to document.
3. Use CARE: Ownership Transfer Request case template.
4. Select Device Ownership Transfer from the eCommerce transactions drop-down.
5. Enter the TSN to transfer and follow the onscreen instructions to complete the transfer process. Make sure the old customer name and the new customer name are correct.
6. Copy the confirmation message and paste it in your case notes.
7. Go back to the customer's account page to verify if the new TSN has populated under Assests (TSNs) and Service Contract section.
Note: If you encounter error when processing the transfer, make sure you carefully fill out the ownership transfer case template, include the error message in your case notes and escalate the case to ACS in Medium priority. Inform the customer they will receive an email once the device is transferred to their account.
8. Inform the new owner they can access their My Account to update their information.
Note: The new transferred device may be visible in My Account between 15 minutes to 2 hours.
3. Categorize and dispose the case accordingly.
4. Send an email to the customer with the case number and the self-service option for reference.

## BIlling Management (Update CC)
Opening: "Thank you for calling TiVo. My name is _____. May I have your name please?"
Account Lookup:
Account auto-populate.
1. Verify the email address.
2. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Account is not auto-populate.
1. Get the caller’s name and phone number to search for the account.
2. Once the account is found, verify the email address.
3. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Few reminders before updating the customer’s credit card information.
1. When updating or changing the credit card, always ask the customer if the billing address is current. This is to make sure that the billing address is correct/current to avoid address verification errors, update if necessary.
Sample verbiage: “Is your address on file, (state the address on the account) the same as the billing address for this credit card?”.
Note: We do not accept PO box for the billing address.
If the customer has a PO Box address on their credit card, ask for a different card with a residential billing address.
If the customer does not have a different credit card, suggest to change the PO box address to a residential billing address from their bank or credit card provider.
2. If the customer owes an outstanding balance, it will be charged when you enter the new credit card information.
3. During an Ownership Transfer it is important that the new customer’s credit card is not updated until the Ownership Transfer is complete and no longer on the old owner’s account. Once we verified the TSN is associated to the new owner’s account we can then begin a credit card update, if necessary. If this is not done in the correct order, the old customer could inadvertently get a confirmation email stating their credit card has been updated when they did not request one.
4. TiVo only accepts US based and non-prepaid credit cards.
Process in updating the credit card:
1. Create a Care case and fill in the subject.
2. Categorize using Category Level 1: Change Credit Card. Select Save.
3. Associate the TSN to the case.
4. Fill out the CARE: Standard Care Template.
5. Select Payment Method Change from the eCommerce drop-down menu.
6. Select Add a new card. Gather the customer's information and be sure to repeat all credit card information back to the customer to verify.
7. Put a check mark on I understand and agree to the User Agreement and Privacy Policy.
8. Ask the customer if they would like to update all contracts on the account to use the new credit card information. Check the Yes, I would like to apply this payment method to all my devices and services box if customers want to update all contracts. Otherwise, leave the box empty if it only applies to one device/contract only.
Notes:
• Credit Card Security (PCI Compliance): To not have any credit card information recorded on the call; you MUST click on the credit card update tab prior to you or the customer speaking any credit card information including the name on the card, credit card #, the expiration date and the security code.
• When gathering the credit card information from the customer, do not enter/type the information outside the credit card screen. Enter the information on the the designated field only.
• Refrain from verbally reiterating, mentioning or saying the customer’s complete or full credit card number again. If you were unable to capture the information, ask the customer to repeat it.
• You MUST enter the customer's name (including middle name or initial) exactly as it appears on the credit card. If you don't, the transaction will be refused.
• If you do not have all of the customer's information in the Account Information section of the Details of their account, you may get an error. Especially check the "Heard From Be Specific" section.
9. Double check all of the information is correct with the customer, and click Save.
10. Inform the customer that a case number will be sent via email along with the self-service option for reference.
11. Close the case with proper disposition and categorization.
Additional reminders:
• For all service interruptions and re-activations, advise the customer to force a connection to the TiVo service. This is so the TiVo device knows that the service has been updated.
• Explain to the customer that DVR service updates can take between 15 minutes to 1 hour, advice the customer to wait 15 minutes and then force a connection to the TiVo service. If after two hours it does not show it is activated/updated, advise them to call TiVo Customer Support.
• If the customer request and insistent to delete their credit card on file, follow the steps below:
To remove a credit card from the customer's account, the customer needs to log in to My Account.
1. On the Account Overview landing page, click the three horizontal line to pull up more options.
2. Select Payment Method.
3. Select Manage Payment Methods.
4. To remove a card, click Remove. The customer can delete multiple cards that are not associated to a contract.

## Order Tracking
Opening: "Thank you for calling TiVo. My name is _____. May I have your name please?"
Account Lookup:
Account auto-populate.
1. Verify the email address.
2. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Account is not auto-populate.
1. Get the caller’s name and phone number to search for the account.
2. Once the account is found, verify the email address.
3. If the caller is unable to verify the email address on file, ask either of the following: Mailing Address Last 4 of the TSN Last 4-digit of the CC
Customer wants to check the status of the order:
1. Create a CARE case, click Next.
2. Enter a subject line and save the case.
3. Use CARE: General Care case temple.
4. To check the status of the order, go to Order section.
5. Click the order link, look for the tracking number under Order Line Item.
6. Verify if TSN/Tracking Number is available:
Tracking number is available:
a. Click the tracking number, you will be directed to the FedEx website delivery page.
b. Check the status of the delivery and provide it to the customer.
c. Provide the tracking number to the customer to track the order.
No tracking number available:
a. Verify if the order is more 24-hours after it is processed.
If yes, consult L2.
If no, educate the customer to check the email within 24 hours for the tracking number.
Note: Orders will not ship on the weekends and Federal holidays.
3. Inform the customer that a case number will be sent via email along with the self-service option for reference.
4. Close the case with proper disposition and categorization.