## Leslie
Task(s) & Milestones | Desctiption | Assignee | Start Date | End Date | Duration | Status | Comment
1. Intro Call (1 Week) |  |  | 2024-12-16 | 2024-12-18 |  | Done
a. Intro call with Wave iX team (internal call) | i.e. all participants partner, PMO, Pavel & Eric. | Wave iX Team | 2024-12-16 | 2024-12-16 | 1 | Done
b. Intro call with client - Kick off and POC identification | i.e. what value we are delivering with the proposed solution. | Wave iX Team,Client | 2024-12-18 | 2024-12-18 | 1 | Done
c. Present Listen Mode Data to client | showcase them possession of the calls traffic | Wave iX Team/Client | 2024-12-18 | 2024-12-18 | 1 | Done
a. Identify Stakeholders | i.e. Roles and Responsibilities from Client and Wave iX end. | Wave iX Team | 2024-12-18 | 2024-12-18 | 1 | Done
2. Discovery Workshop (2 Week) |  |  | 2024-12-18 | 2025-01-27 |  | Done
a. Gather Operational Requirements | i.e. Document client’s IVR, FAQs, operational workflows and gather other supporting materials and documentation from Client services or Operations | Wave iX Team, CS, Ops | 2024-12-18 | 2024-12-18 | 1 | Done
b. Identify Key Operational Pain Points | i.e. Highlight areas for improvement | Wave iX Team, CS, Ops | 2024-12-19 | 2024-12-19 | 1 | Done
c. Use Case identification that needs to be automated. | Propose set of usecase to client that can be automated and get beneficial. | Wave iX Team/Client | 2024-12-20 | 2024-12-21 | 2 | Done
d. Identify Call routing Flows | All ivr detials gathered from telephony | Wave iX Team | 2025-12-23 | 2025-12-24 | 2 | Done
e. Identify Routing destinations | i.e. endpoints of each call scenario in IVR | Wave iX Team | 2025-01-02 | 2025-01-17 | 16 | Done
f. Detailed Usecase steps from Operations | need detailed step by step of each flow right from the call receiving and involving steps in the CRM | Wave iX Team/Operations | 2025-01-20 | 2025-01-27 | 8 | Done
g. Identify FAQs | need to collect and en-scope FAQ(s) that needs to be automated by IVR Bot. It can be available on pubic forum or Operations can guide us | Wave iX Team/Operations | 2025-01-20 | 2025-01-27 | 8 | Done
3. Tech Discovery (1 Week) |  |  | 2025-01-02 | 2025-02-10 |  | Done
a. Tech sessions for understanding client platform (if required) | e.g. CCaas? CRM? KB? - This information may be available during sales process. | Wave iX Team/Client | 2025-01-02 | 2025-01-03 | 2 | Done
b. Assessment of the platform and see if we need to develop customizations for the enablement. | Wave iX team will check if we have out of the box integration solution or do we need to develop customize code | Wave iX Team | 2025-01-06 | 2025-01-07 | 2 | Done
c. Collect URLs VoIP/Https from both end to whitelist | For establishing the Secure communication whitelisting from both ends needs to be done. Genesys & wave IX , Wave IX and CRM | Wave iX Team | 2025-01-08 | 2025-01-08 | 1 | Done
g. Get API Access from source CCaaS, CRM, KB i.e. User Creation | Access provision from the on the CCaaS, CRM, KBs. | Wave iX Team/Client | 2025-01-16 | 2025-01-16 | 1 | Done
g. Standard API and end points | gather required APIs | Wave iX Team/Client | 2025-01-13 | 2025-02-03 | 22 | Done | Client is currently working on providing Boomi API
g. Get API documentation | Access provision from the on the CCaaS, CRM, KBs. | Wave iX Team/Client | 2025-01-13 | 2025-02-03 | 22 | Done | Client is currently working on providing Boomi API
g. Gather Order Status Details | i.e. different types of order tracking statuses being used in MAO | Wave iX Team/Client | 2025-01-24 | 2025-01-24 | 1 | Done
g. Clarify order number & LOB identification criteria |  | Wave iX Team/Client | 2025-01-24 | 2025-01-24 | 1 | Done
f. Review API Documentation and prepare questions | documentation of CRMs, ACDs etc | Wave iX Team | 2025-01-27 | 2025-02-03 | 8 | Done
e. System Architectural Diagram | i.e. diagram to visually analyze the configuration scenario | Wave iX Team/Ops | 2025-01-15 | 2025-01-22 | 8 | Done
h. Initiate Tech Session with Client on Mapping Usecases with APIs | Initiate Tech Session with Client on Mapping Usecases with APIs | Wave iX Team/Operations | 2025-01-30 | 2025-01-31 | 2 | Done
i. Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Wave iX Team/Client | 2025-01-28 | 2025-02-10 | 14 | Done | need to connect with wasiq and ask him to check what use cases out of the list could have been automated
d. Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Wave iX Team | 2025-01-15 | 2025-01-22 | 8 | Done
e. Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Wave iX Team | NA | NA |  | Not Applicable
4. Listen Mode Enablement(3weeks) (if required)
a. Assess Telephony Requirements | i.e. DID creation, Call Forwarding | Wave iX Team | 2025-11-05 | 2025-11-06 | 2 | Done
b. Plan Telephony Integration | i.e. raise formal tickets or request | Wave iX Team | 2025-11-07 | 2025-11-10 | 4 | Done
c. Implement Telephony Integration | Implement Telephony Integration | Wave iX Team | 2025-11-11 | 2025-11-11 | 1 | Done
d. Integration Testing | i.e. make Test Calls E2E and monitor logs, take Go-No Go | Wave iX Team | 2025-11-11 | 2025-11-11 | 1 | Done
e. Enablement of Listening Mode | Enablement of Listening Mode | Wave iX Team | 2025-11-12 | 2025-11-25 | 14 | Done
5. Listen Mode Data Analysis |  |  |  |  | 1
Collect Data and build Analytics |  | BI | 2025-11-26 | 2025-11-27 | 2 | Done
Use case identification, |  | BI | 2025-11-28 | 2025-12-01 | 4 | Done
Draw Flows, understanding Flows |  | BI | 2025-12-02 | 2025-12-05 | 4 | Done
6. Integration in Telephony i.e. SIP or PSTN (2 Weeks) |  |  | 2025-01-10 | 2025-02-26 |  | In-Progress
a. Assess Telephony Requirements |  | Wave iX Team | 2025-01-10 | 2025-01-13 | 4 | Done
b. Plan Telephony Integration |  | Wave iX Team | 2025-01-13 | 2025-01-14 | 2 | Done
c. Implement Telephony Integration |  | Wave iX Team | 2025-01-21 | 2025-01-23 | 3 | Done
d. Test Telephony Integration |  | Wave iX Team | 2025-01-24 | 2025-01-25 | 2 | Done
e. Enable call forwarding to Wave iX |  | Wave iX Team | 2025-02-24 | 2025-02-25 | 2 | To-Do
f. Thorough Testing of call forwarding |  | Wave iX Team | 2025-02-25 | 2025-02-26 | 2 | To-Do
7. Setup Routing Skill |  | Wave iX Team | 2025-02-03 | 2025-02-15 |  | Done
a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-15 | 12 | Done | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-15 | 12 | Done | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-15 | 12 | Done | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-15 | 12 | Done | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-15 | 12 | Done | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this | 3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
8. Setup Knowledge Skill |  |  | 2025-02-03 | 2025-02-10 |  | Done
a. Define and Emphasize Source-Only Retrieval |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
b. Filter Questions to Resolve Ambiguities |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
c. Agent Role and Company Context |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
d. Consistent Prompt Framework |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
e. Source Formatting |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
f. Logical Grouping of Sources in Collections |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
g. Content Length |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
h. Adapt Content for Telephony |  | Wave iX Team | 2025-02-03 | 2025-02-10 | 8 | Done
9. Setup Custom Skill |  |  | 2025-02-10 | 2025-02-15 |  | Done
a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-10 | 2025-02-15 | 5 | Done | our dev team will be able to do this
b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-10 | 2025-02-15 | 5 | Done | our dev team will be able to do this
1. Instruct BOT |  | Wave iX Team | 2025-02-10 | 2025-02-15 | 5 | Done | our dev team will be able to do this
2. Configuring API Call |  | Wave iX Team | 2025-02-10 | 2025-02-15 | 5 | Done | our dev team will be able to do this
3. Adding Parameters |  | Wave iX Team | 2025-02-10 | 2025-02-15 | 5 | Done | our dev team will be able to do this
10. Setup BOT AI Agent |  |  | 2025-01-21 | 2025-02-10 |  | Done
a. AI Agent(bot) Development - by CXD | using Studio, build a BOT AI agent and assign Task | Wave iX Team | 2025-01-21 | 2025-02-10 | 21 | Done
b. CX Design: Integrate knowledge sources |  | Wave iX Team | 2025-01-24 | 2025-02-10 | 18 | Done
c. CX Design: Set up simulations and evaluations |  | Wave iX Team | 2025-01-28 | 2025-02-10 | 14 | Done
d. CX Design: AMP Prompt Engineering |  | Wave iX Team | 2025-01-28 | 2025-02-10 | 14 | Done
11. Integration Backend System (2 Weeks) | i.e. Wave iX services Integration with CCaaS's and CRM's APIs. |  | 2025-02-14 | 2025-02-24 |  | In-Progress
c. Implementation of Use Cases in Wave iX and Integration Feedback | Implementation of Use Cases in Wave iX and Integration Feedback | Wave iX Team | 2025-02-14 | 2025-02-20 | 7 | Done
d. Product Increment Review & Retro | demo | Wave iX Team | 2025-02-20 | 2025-02-21 | 2 | Done
e. Go-No Go. Sign Off | Go-No Go. Sign Off | Wave iX Team | 2025-02-24 | 2025-02-24 | 1 | To-Do
12. QA & QC |  | Wave iX Team | 2025-02-12 | 2025-02-26 |  | In-Progress
a. Develop Test case for Testing AI BOT |  | Wave iX Team | 2025-02-12 | 2025-02-26 | 15 | In-Progress
a. BOT Testing |  | Wave iX Team | 2025-02-12 | 2025-02-26 | 15 | In-Progress
c. Define Centralized Space for Reporitng and sharing Bugs |  | Wave iX Team | 2025-02-12 | 2025-02-26 | 15 | In-Progress
d. Bug Fixing & Regression Testing |  | Wave iX Team | 2025-02-12 | 2025-02-26 | 15 | In-Progress
e. Go-No Go. Sign Off | Go-No Go. Sign Off | Wave iX Team | 2025-02-12 | 2025-02-26 | 15 | To-Do
13. User Acceptance Testing & Optimization |  |  | 2025-02-25 | 2025-02-28 |  | To-Do
a. Identification of Test Case with the help of CS & Ops. | Ops will come up with the pre-defined test cases | Ops | 2025-02-25 | 2025-02-26 | 2 | To-Do
b. Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Wave iX Team | 2025-02-27 | 2025-02-28 | 2 | To-Do
b. Schedule and Conduct Session for testing on Official Bridges. | Schedule and Conduct Session for testing on Official Bridges. | Wave iX Team | 2025-02-27 | 2025-02-28 | 2 | To-Do
c. Review Results with Wave iX Team | Review Results with Wave iX Team and see if we need to develop | Wave iX Team | 2025-02-28 | 2025-02-28 | 1 | To-Do
Go-No Go Sign Off from Project Team |  |  | 2025-02-28 | 2025-02-28 | 1 | To-Do
14. Go-Live - Phase 1 |  |  | 2025-03-03 | 2025-03-05 |  | To-Do
a. Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Wave iX Team | 2025-03-03 | 2025-03-04 | 2 | To-Do
b. Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Wave iX Team | 2025-03-04 | 2025-03-04 | 1 | To-Do
c. Bridge Reservation and Go-Live | Bridge Reservation and Go-Live | Wave iX Team | 2025-03-04 | 2025-03-04 | 1 | To-Do
d. Go-Live |  | Wave iX Team | 2025-03-05 | 2025-03-05 | 1 | To-Do
e. Monitoring bridge | Monitoring bridge | Wave iX Team | 2025-03-05 | 2025-03-05 | 1 | To-Do
15. Ongoing Testing and Review of Conversations in AMP |  |  | 2025-03-06 | 2025-03-12 |  | To-Do
a. Adaptation | retrospective | Wave iX Team | 2025-03-06 | 2025-03-10 | 5 | To-Do
b. Refinements | Refinements | Wave iX Team | 2025-03-11 | 2025-03-12 | 2 | To-Do
Phase 2 Implementation
1. User Acceptance Testing & Optimization |  |  | 2025-03-12 | 2025-03-17 |  | To-Do
a. Identification of Test Case with the help of CS & Ops. | Ops will come up with the pre-defined test cases | Ops | 2025-03-12 | 2025-03-13 | 2 | To-Do
b. Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Wave iX Team | 2025-03-14 | 2025-03-14 | 1 | To-Do
b. Schedule and Conduct Session for testing on Official Bridges. | Schedule and Conduct Session for testing on Official Bridges. | Wave iX Team | 2025-03-17 | 2025-03-17 | 1 | To-Do
c. Review Results with Wave iX Team | Review Results with Wave iX Team and see if we need to develop | Wave iX Team | 2025-03-17 | 2025-03-17 | 1 | To-Do
Go-No Go Sign Off from Project Team |  |  | 2025-03-17 | 2025-03-17 | 1 | To-Do
2. Go-Live - Phase 2 |  |  | 2025-03-17 | 2025-03-18 |  | To-Do
a. Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Wave iX Team | 2025-03-17 | 2025-03-17 | 1 | To-Do
b. Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Wave iX Team | 2025-03-17 | 2025-03-17 | 1 | To-Do
c. Bridge Reservation and Go-Live | Bridge Reservation and Go-Live | Wave iX Team | 2025-03-17 | 2025-03-17 | 1 | To-Do
d. Go-Live |  | Wave iX Team | 2025-03-18 | 2025-03-18 | 1 | To-Do
e. Monitoring bridge | Monitoring bridge | Wave iX Team | 2025-03-18 | 2025-03-18 | 1 | To-Do
3. Ongoing Testing and Review of Conversations in AMP |  |  | 2025-03-20 | 2025-03-25 |  | To-Do
a. Adaptation | retrospective | Wave iX Team | 2025-03-20 | 2025-03-22 | 3 | To-Do
b. Refinements | Refinements | Wave iX Team | 2025-03-24 | 2025-03-25 | 2 | To-Do
Formulas:
Start Date = [Start Date, row below]
End Date = [End Date, row below]

## Routing & Ques
LOB Name | Main Menu | Sub menu | End Point | Genesys Queue Name | Que Receiving PVT Number | Queue Type | Hoops Weekdays | HOOPS Weekends | Hoops Weekdays | HOOPS Weekends
Leslie's Pool
Primary DID +1 703-540-4401 | Press 1 New Service Appointment | Repair and Installation | -
Backup DID +1 703-662-8467 |  | Press 1 to New Appointment | Route to Agent | Leslies_NewServiceAppt-3577 | 18442016 | Service | 10-7p ET | 10-7p ET
|  | Press 2 to Change Appointment | Route to Agent | Leslies_ExistingServiceAppt-3577 | 18442012 | Service | 10-7p ET | 10-7p ET
Testing DID 1703-662-8481 |  | Press 3 to Cancel Appointment | Route to Agent | Leslies_ExistingServiceAppt-3577 | 18442012 | Service | 10-7p ET | 10-7p ET
Deflection 18442023 |  | Press 9 to repeat menu
Receiving 18442024 |  | Press # to return to main menu
| Press 2 Commercial Orders & Inquiries |  | Transfer to 602-366-3792 |  | 18442011
| Press 3 Hot Tubs |  | Transfer to 602 366 3790 |  | 18442013
Press 4 New & Exisitng Orders
New / Existing Order
|  | Press 1 New Order | Route to Agent | Leslies_NewOrder-3577 | 18442014 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
|  | Press 2 Existing Order | Route to Agent | Leslies_ExistingOrder-3577 | 18442010 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
Press 9 to repeat menu
Press # to return to main menu
Press 5 LP Perks Rewards Program
POOL PERKS
|  | Press 1 Password Reset | Route to Agent | Leslies_CS-3577 | 18442008 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
|  | Press 2 Pool Perk reward questions | Route to Agent | Leslies_CS-3577 | 18442008 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
Press 9 to repeat menu
Press # to return to main menu
| Press 6 AccuBlue |  | Transfer to 602 931 4934 |  | 18442009
Press 7 All Other CS Inquiries
CUSTOMER SERVICE
|  | Press 1 to speak to customer care rep | Route to Agent | Leslies_CS-3577 | 18442008 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
Press 9 to repeat menu
Press # to return to main menu
| Press 8 Company Directory |  | Transfer to 602 931 4914 |  | 18442015
| Press 9 If a Leslies Pool Employee |  | Transfer to 602 931 4928 |  | 18442017
Press # to repeat the menu
LOB Name | Main Menu | Sub menu | End Point | Genesys Queue Name |  | Queue Type | Hoops Weekdays | HOOPS Weekends | Hoops Weekdays | HOOPS Weekends
In the Swim
Primary DID +1 703-540-4402 | Press 1 Commercial Orders and Inquiries |  | Transfers 630-447-6491 |  | 18442019
Backup DID +1 703-662-8468 | Press 2 New Order |  | Route to Agent | InTheSwim_NewOrder-3577 | 18442006 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
| Press 3 Existing Orders |  | Route to Agent | InTheSwim_ExistingOrder-3577 | 18442004 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
Testing DID 1703-662-8482 | Press 4 Customer Service |  | Route to Agent | InTheSwim_CS-3577 | 18442002 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
Deflection 18442025 | Press 9 to listen to menu again |  | Repeat menu
Receiving 18442026
LOB Name | Main Menu | Sub menu | End Point | Genesys Queue Name |  | Queue Type | Hoops Weekdays | HOOPS Weekends | Hoops Weekdays | HOOPS Weekends
Pool Supply World
Primary DID +1 703-540-4403 | Press 1 If you know your parties Extension |  | Transfer to 602 366 3792 |  | 18442021
Backup DID +1 703-662-8480 | Press 2 Place a new order |  | Route to Agent | PoolSupplyWorld_NewOrder-3577 | 18442002 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
| Press 3 Existing Order |  | Route to Agent | PoolSupplyWorld_ExistingOrder-3577 | 18442020 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
| Press 4 Customer Service |  | Route to Agent | PoolSupplyWorld_CS-3577 | 18442018 | Ecomm | 8a - 8p EST | 8a - 7p EST Sat and 9a - 6p ET Sun | 8a - 7p EST | 8a - 7p EST
Testing DID 1703-662-8483 | Press 9 to listen to menu again
Deflection 18442027
Receiving 18442028

## Use Cases
Use Case | Input | Expected Response
Retrieve Shipping Status | Order # | Current Shipping Status
Failed Order - Complete payment | Order # | Payment Processing - Chase
Retrieve Freight Shipping Status | Order # | Current Shipping Status - various shippers need to be able to identify the shipper in MAO and provide information to customer
Fraud Hold | Order # | Advise there is currently a hold on the order and to check their email from our Fraud team to confirm details

## Scenarios
CNT | Call Driver | Scenario | Sample Case/s | Tool/s Utilized | Process | Visibility |  | Resolution
[6 empty] | Tier 1 | Tier 2 | Tier 1 | Tier 2
1 | Retrieve Shipping Status | • Customer is asking regarding the status of the order or when it will be shipped/delivered. • Customer is wondering why the order was delayed/lost in transit. | 4661663 | MAO & FedEx Website (Leslie's Primary Carrier) and other carriers | • Open MAO to check tracking information. • A hyperlink is normally associated to the tracking number of the order. Click on the hyperlink and the system will route to the FedEx website (or other carriers) to check latest updates of the movement. | ✓ |  | ✓
2 | Failed Order - Complete Payment | • Customer called in to report that there were no confirmation received after placing an order with help of the CSA. • Customer called back because charges related to the order has been taken from their card but still no confirmation received; no visible order when CSA cheched on MAO. | 4612218 | MAO | • Ask order number from customer. • Locate the order through MAO using the order number with the correct organization. • Hit on View Order Status to check the order details. • For failed order, Tier 1 agents don't have the visibility of the reason as to why the order failed. Hence, case should be created and transfer to Tier 2. | ✓ | ✓ |  | ✓
3 | Retrieve Freight Shipping Status | • Customer called to check the status of the order/s (custom-made items and heavy equipment only). • Customer is asking why it took to long to ship and deliver the order (custom-made items and heavy equipment only). | 4657607 | MAO & SPS Commerce | • Ask for the order number and locate the order through MAO. • Get the reference number (Rel No.) that normally starts with MA and using SPS Commerce tool. Hit on the Fulfillment Monitor twice and input the reference number under contain. • Therafter, shipping information for freight order will appear. | ✓ |  | ✓
4 | Fraud Hold | • Manual Fraud Cancel - Customer inquiring about the recent order that was cancelled even though it was successfully placed it is because the billing information and cc information did not match. (cx will just have to re-enter payment information for verification) • Fraud Cancel - Customer inquiring about the recent order that was cancelled even though it was successfully placed it is because the billing information and cc information did not match. (cx needs to reprocess the order) • Manual Fraud Review - Customer claims they are seeing a fraudulent transaction on their credit card, because they did not shop with us. - If the customer is seeing multiple charges, but does recognize a Leslie’s purchase, look for duplicate orders. | 4611133 | MAO & SF Service Cloud | • Fraud Hold visibility can be checked through MAO by getting the order number. • Resolution wise, this is out of scope for Tier 1 agents. • For that reason, case will be created and should be transferred to Tier 2 (Customer Escalation Queue) - tag Kara Scholl or Jamie Russ (KB 1492). |  | ✓ |  | ✓

## MAO Order Status
Core | State | Status Category | Remark | Agent Response
1000 | Open | Intermediatory | Newly-created orders | No specific spiel - Agent informs customers that orders has been placed in the system
1500 | Back Ordered | Intermediatory | No available item in the inventory | Thank you for patiently waiting. I’ve looked through our inventory and see the item is on back order. Unfortunately, I’m unable to provide you with a shipping date. However, once the item is available for shipping, you should receive an email with the tracking number. If you don’t want to wait for the item, I will be happy to cancel the order for you and your card will not be charged. How would you like to proceed?
2000 | Allocated | Main | Order has been confirmed through the order management system, information has not yet been set to the warehouse. Orders are typically allocated for 1 hour (The Grace Period) | Agent informs customers that order information is yet to be sent to the warehouse. Order is confirmed but information has not been sent to the warehouse yet. There is a one-hour grace period for Allocated status which allows the customer to cancel. | Partially + Status Customer has multiple orders/bulk orders; some items have completed; some are pending
3000 | Partially Released, Released | Main | Order information has been sent to the Warehouse, the picking and packing process has been started. Order should be in this phase for 24-48hours | No specific response
3500 | In Process | Intermediatory
3600 | Partially Picked, Picked | Intermediatory | Confirmed picked up orders | No specific spiel - Orders are picked up.
3700 | Partially Packed, Packed | Intermediatory | Confirmed packed orders; ready for pick up | No specific spiel - Informs that order/s have been packed and is ready for pick up.
7000 | Partially Fulfilled, Fulfilled | Main | Order is in the carriers possession and is either in transit or has already been delivered. At this time the customer is officially charged for their order. | No specific spiel - Agent informs that the order is in carrier's posession; order can be in transit or delivered.
7500 | delivered | Intermediatory
8500 | Partially Returned, Returned | Intermediatory | Unit/item has been returned to Leslie's, In the Swim | No specific spiel - Agent informs that item has been successfully returned to Leslie's.
8000 | Partially Pending Return, Pending Return | Intermediatory | Replacement has been processed; shipping label has been sent out; waiting for the original item to be returned | No specific spiel - Agent assists the customer to process replacement; shipping label has been generated to be used to return the item.
9000 | Canceled | Main |  | Order was cancelled and is not going to be fulfilled
18000 | Partially Returned, Returned | Intermediatory | Unit/item has been returned to Leslie's, In the Swim | No specific spiel - Agent informs that item has been successfully returned to Leslie's.
11000 | Partially Pending Return, Pending Return | Intermediatory | Replacement has been processed; shipping label has been sent out; waiting for the original item to be returned | No specific spiel - Agent assists the customer to process replacement; shipping label has been generated to be used to return the item.
13000 | Partially Pending Approval, Pending Approval | Intermediatory | For Leslie's team confirmation | No specific spiel
19000 | Return Canceled, Return Canceled | Intermediatory
15000 | Partially Received, Received Return | Intermediatory | Customer received the item | No specific spiel - Customer has received the item; can also be validated thru the tracking number.

## MAO Order No
Orders typically have 10 digits, first 3 are letters, last seven are numeric.
WLE – Leslie’s Endless Aisle (store ordered for customer)
WLP – Leslie’s Website or customer care placed order
WIT – In the Swim website or customer care placed order
WPR – Leslie’s Pro
Sample Order IDs
WLE: WLE0384127
WLP: WLP1873931
WIT: WIT0645702
WPR: WPR9080512

## MAO Sandbox
https://lesls-auth.omni.manh.com/discover_user#/order email: bilal.khalid@ibex.co Leslies@123 Merchant ID – 700000012993 we use for DEV testing. https://development-na01-lesliespoolmart.demandware.net/on/demandware.store/Sites-Site/default/ user: bilal.khalid@ibex.co pass: MegamanxLeslies@ibex

## Sip
Wave iX
SIP URI is sip:leslies-pools.voip.parloa.us phone number to dial in to is (928) 492-6245.

## Boomi API
Staging | Prod
curl --location 'https://api.lesl.dev:443/ws/rest/Manhattan/OrderStatus/26835473' \ --header 'Authorization: Basic TW9iaWxlQXBwQGxlc2xpZXNwb29sbWFydC1OODNKVTU6N2NmYTU4MzItZDJiYS00OTk3LWFkYjctMmUyZDgxY2NlZjk2' | curl --location 'https://api.lesl.cloud:443/ws/rest/Manhattan/OrderStatus/27017348' \ --header 'Authorization: Basic TW9iaWxlQXBwQGxlc2xpZXNwb29sbWFydC1OODNKVTU6N2NmYTU4MzItZDJiYS00OTk3LWFkYjctMmUyZDgxY2NlZjk2'