## Action Plan
Mint Mobile Action Plan
Key Stakeholders
| Flip |  |  | Ibex |  |  | Mint
| Project Lead | Yan Marchenko |  | Project Lead | Sinnan |  | Project Lead
| Product Lead | Will Van der Linde |  | Product Lead | Wasiq |  | Product Lead
| Telephony Lead | Joe Garlick |  | Telephony Lead | Sinnan/Wasiq |  | Telephony Lead
| Executive Sponsor | Sam Krut |  | Executive Sponsor | Eric Guarro |  | Executive Sponsor
Key Systems/Integrations
Phone System | Genesys Pure Cloud
Bespoke System
Helpdesk
OMS
Chat Support
TTS Provider
Messaging
Implementation Milestones
Phase | Timeline | Milestone
1 | weeks 1 | Architectural Design & Integration
2 | week 2 | Testing & Goals Alignment
3 | week 3 | Initial Automation Enablement
4 | week 4-5 | Secondary Automation Enablement
Intent Enablement
Phase | Timeline | Milestone
Primary | Week 3 | Account_Verification, Sim_Activation, Check_Account_Info, Transfer_Number_In
Secondary | Weeks 4-5 | Discontinue_Service, Transfer_Number_Out, Phone_Hardware_Issue, Login_Issue
Tertiary | Weeks 6-7 | TBD
Milestones Breakdown
Due Date | Key Theme |  | Action |  | Owner | Status | Testing Criteria | Testing Status
Iniciation |  |  | Milestone 1 : Architectural Design & Integration
Client Coordination
Client approval
admin access
Flip CX Meetup
Week 1 |  |  | Milestone 1 : Architectural Design & Integration
| Phone System Integration |  | Perform Phone System Integration |  | Joe | In Progress | Are calls properly being forwarded to Flip and forwarded back to the agent if necessary? Are call recordings available? Are there any latency issues in response time? | Tested - Success
| Listen Mode Launch |  | Launch Listen Mode |  | Yan | Complete | Ensure Flip greeting is as expected and is forwarding calls after it captures the intent | Tested - Success
| Listen Mode Analysis |  | Analyze Listen Mode Results to determine intent distribution |  | Yan | Complete |  | N/A
| Implement/test new classifier library |  | Configure and then test effectiveness of upfront telco classifier |  | Joe | To-Do | Ensure classifier accuracy and detection of above 97% | Not Started
| Recurring Cadences |  | Setup biweekly Cadence for data insights reviews |  | Yan | To-Do |  | N/A
| Systems Integration Discovery |  | Conduct discovery to understand key systems at play (OMS, SMS, etc.) |  | Will / Joe | In Progress |  | N/A
| API Validation 1.1 |  | Ensure all neeeded API endpoints are exposed to provide automation on initial intents |  | Will / Joe | In Progress | Are we receiving any errors on API calls? Are we receiving any integration errors? | Not Started
| Systems API Documentation |  | Retrieve and Share any Available API Documentation |  | IBEX | To-Do |  | N/A
| Mint Mobile User Test Accounts |  | Mint/IBEX to provide test Mint accounts for API testing purposes |  | IBEX | To-Do |  | N/A
| CX Validation 1.1 |  | Develop and agree upon key customer experience flows for initial intents and configurations. Including SMS Scripting and upfront customer disclosure |  | Yan/Will | In Progress | Conduct walkthrough and sign off of key flows | Not Started
| Opt Out Disclosure |  | open item: opt out discloure from Mint Mobile |  | Ibex | To-Do
Week 2 |  |  | Milestone 2 : Testing & Goals Alignment
| KPI Alignment |  | Align on key testing criteria KPIs to measure current performance of existing systems and call center, automation impact, and CX success |  | IBEX/FLIP | To-Do | Were respective KPIs reached across different focus areas (AHT, agent seats, etc.) | Not Started
| External Reporting Analytics |  | Develop external analytics and performance dashboard access |  | Flip | To-Do | Ensure data accuracy, test latency, and ensure consistency to Flip portal | Not Started
| System Hand Over |  | Hand over system to Ibex/Mint for approval |  | Yan | To-Do |  | N/A
| Final Sign-off |  | Conduct final review and confirmation of plan prior to go live |  | Ibex/Mint | To-Do |  | N/A
| Call center communication |  | Ibex to communicate rollout changes to agents (helpful handoff, how we hand off) |  | Ibex | To-Do |  | N/A
Week 3 |  |  | Milestone 3 : Initial Automation Enablement
| Verification & Intent Enablement |  | Enable account verification and initial intent automation in the portal (sim_activation, check_account_info, transfer_number_in) |  | Yan | To-Do | Call in to test functionality and ensure all configurations are working effectivley | Not Started
| Intent Monitoring |  | Monitor success of initial intents and make configuration tweaks to improve performance (if needed) |  | Yan | To-Do | Compare early automation numbers across averages and make sure results are within the standard deviation | Not Started
| Hypercare |  | Monitor actions completed by the AI and ensure accuracy and completion of tasks, track feedback from customers and agents |  | Yan/Will/Joe | To-Do | Review internal tracking logs, ensure no errors occur across AI actions | Not Started
| Intent Identification |  | Identify more complex intents to enable future automation |  | Yan | To-Do |  | N/A
| API Validation 1.2 |  | Ensure all neeeded API endpoints are exposed to provide automation on secondary intents |  | Will / Joe | To-Do | Are we receiving any errors on API calls? Are we receiving any integration errors? | Not Started
| CX Validation 1.2 |  | Develop and agree upon key customer experience flows for secondary intents |  | Yan/Will | To-Do | Conduct walkthrough and sign off of key flows | Not Started
Week 4-5 |  |  | Milestone 4 : Secondary Automation Enablement
| Intent Enablement |  | Enable secondary intent automation in the portal (discontinue_service, transfer_number_out, phone_hardware_issue, login_issue) |  | Yan | To-Do | Call in to test functionality and ensure all configurations are working effectivley | Not Started
| Intent Monitoring |  | Monitor success of complex intents and make configuration tweaks to improve performance (if needed) |  | Yan | To-Do | Compare early automation numbers across averages and make sure results are within the standard deviation | Not Started
| Hypercare |  | Monitor actions completed by the AI and ensure accuracy and completion of tasks, track feedback from customers and agents |  | Yan/Will/Joe | To-Do | Review internal tracking logs, ensure no errors occur across AI actions | Not Started
| Intent Identification |  | Identify more complex intents to enable future automation |  | Yan | To-Do |  | N/A
| API Validation 1.3 |  | Ensure all neeeded API endpoints are exposed to provide automation on tertiary intents |  | Will / Joe | To-Do | Are we receiving any errors on API calls? Are we receiving any integration errors? | Not Started
| Systems Integration Dev Requests |  | Scope out and enable any more complex integrations (if needed) |  | Will | To-Do | Ensure integration is not running any errors and meets the anticipated outcomes | Not Started
| CX Validation 1.3 |  | Develop and agree upon key customer experience flows for tertiary intents |  | Yan/Will | To-Do | Conduct walkthrough and sign off of key flows | Not Started
| Recurring Cadences |  | Setup weekly Cadence for data insights reviews |  | Yan | To-Do |  | N/A

## Sheet3
Intent Enablement | Enable secondary intent automation in the portal (discontinue_service, transfer_number_out, phone_hardware_issue, login_issue)
Intent Monitoring | Monitor success of complex intents and make configuration tweaks to improve performance (if needed)
Hypercare | Monitor actions completed by the AI and ensure accuracy and completion of tasks, track feedback from customers and agents
Intent Identification | Identify more complex intents to enable future automation
API Validation 1.3 | Ensure all neeeded API endpoints are exposed to provide automation on tertiary intents
Systems Integration Dev Requests | Scope out and enable any more complex integrations (if needed)
CX Validation 1.3 | Develop and agree upon key customer experience flows for tertiary intents
Recurring Cadences | Setup weekly Cadence for data insights reviews

## Ibex - Exe Plan
# | Tasks | Descirption | Assignee | Start | End | Duration | Status | Comments | Dependencies
Product Pitch
| Pitch WaveIX product suite to Client. | Ibex Sales to Pitch the Product Suite and Services to Client - Define the solution proposal - Define goals & KPIs. - Proposal for API feasibility integration. | Sales | 2024-07-15 | 2024-07-17 | 2 | Closed |  | FS
| Demonstration of Platform | Review Platform and ask necessary questions if required | Project Team | 2024-07-18 | 2024-07-20 | 2 | Closed |  | FS
| Request Admin Access to Platform | Ibex need to get admin access to Client Platform | Project Team | 2024-07-21 | 2024-07-23 | 2 | Closed |  | FS
| Access provisioning | Client to give access and Ibex to authenticate and authorize the access | Client | 2024-07-24 | 2024-07-26 | 2 | Closed |  | FS
| Meetup with Product on the solution | Meetup with the Product Team and discuss the integration | Project Team/Product Team | 2024-07-27 | 2024-07-29 | 2 | Closed |  | FS
| Explore integration options | Product team will explore and discuss the feasibility of the integration | Project Team/Product Team | 2024-07-30 | 2024-08-01 | 2 | Closed |  | FS
| Phone System Integration | Actual integration of Ibex product with the Client platform | Product Team | 2024-08-02 | 2024-08-04 | 2 | Closed |  | FS
Passive Listen Mode Enablement (PLM)
| Client Approval on Enabling PLM | Request client approval on enabling the PLM on client platform | Project Team | 2024-08-05 | 2024-08-07 | 2 | Closed |  | FS
| Listen Mode Launch | Implement and test if the existing production flow is working fine and close | Product Team | 2024-08-08 | 2024-08-10 | 2 | Closed |  | FS
| Listen Mode Analysis & Monitoring | the is a Span where listening mode will be observed and monitored | Product Team | 2024-08-11 | 2024-08-13 | 2 | Closed |  | FS
| Custom Analytics | Product team will develop stats and report based on the PLM | Product Team | 2024-08-14 | 2024-08-16 | 2 | Closed |  | FS
| Review Listen Mode - Internal | review the data captured in PLM | Project Team/Product Team | 2024-08-17 | 2024-08-19 | 2 | Closed |  | FS
| Review Listen Mode - External ( client) | Showcase data of PLM with client | Project Team/Client | 2024-08-20 | 2024-08-22 | 2 | Open |  | FS
| Go-No Go (pahse Closure) | ask client for the phase closure | Client/ Project Team | 2024-08-23 | 2024-08-25 | 2 | Open |  | FS
Automate Intent Enablement Feasibility (Initial)
| Verification & Intent Enablement | Enable account verification and initial intent automation in the portal | Product Team | 2024-08-05 | 2024-08-07 | 2 | Open
| Customer Intent Monitoring | Monitor success of initial intents and make configuration tweaks to improve performance (if needed) | Product Team | 1899-12-31 | 1900-01-02 | 2 | Open
| Hypercare | Monitor actions completed by the AI and ensure accuracy and completion of tasks, track feedback from customers and agents | Product Team | 2024-08-08 | 2024-08-10 | 2 | Open
| Customer Intent Identification | Identify more complex intents to enable future automation | Product Team | 1900-01-03 | 1900-01-05 | 2 | Open
| Intent End points feasibility | Ensure all neeeded API endpoints are exposed to provide automation on secondary intents | Product Team | 2024-08-11 | 2024-08-13 | 2 | Open
| Secondary Intent Identification | Develop and agree upon key customer experience flows for secondary intents | Product Team | 1900-01-06 | 1900-01-08 | 2 | Open
Automate Intent Enablement Feasibility (Secondary)
| Intent Enablement | Enable secondary intent automation in the portal (discontinue_service, transfer_number_out, phone_hardware_issue, login_issue) | Product Team |  |  | 2 | Open |  | FS
| Intent Monitoring | Monitor success of complex intents and make configuration tweaks to improve performance (if needed) | Product Team |  |  | 2 | Open |  | FS
| Hypercare | Monitor actions completed by the AI and ensure accuracy and completion of tasks, track feedback from customers and agents | Product Team |  |  | 2 | Open |  | FS
| Intent Identification | Identify more complex intents to enable future automation | Product Team |  |  | 2 | Open |  | FS
| Intent End points feasibility | Ensure all neeeded API endpoints are exposed to provide automation on tertiary intents | Product Team |  |  | 2 | Open |  | FS
| Systems Integration Dev Requests | Scope out and enable any more complex integrations (if needed) | Product Team |  |  | 2 | Open |  | FS
| CX Validation 1.3 | Develop and agree upon key customer experience flows for tertiary intents | Product Team |  |  | 2 | Open |  | FS
| Recurring Cadences | Setup weekly Cadence for data insights reviews | Product Team |  |  | 2 | Open |  | FS
[6 empty] | 2 | Open |  | FS
<select>
<select>
Active Listen Mode Enablement (ALM)
| Client Approval on Enabling ALM | Request client approval on enabling the ALM on client platform | Project Team | 2024-08-05 | 2024-08-07 | 2 | Open |  | FS
| Listen Mode Launch | Implement and test if the existing production flow is working fine and close | Product Team | 2024-08-08 | 2024-08-10 | 2 | Open |  | FS
| Listen Mode Analysis & Monitoring | the is a Span where listening mode will be observed and monitored | Product Team | 2024-08-08 | 2024-08-10 | 2 | Open |  | FS
| Discuss Reporting Requirements - KPIs | Discuss reporting requirements | Project Team/Product Team | 2024-08-11 | 2024-08-13 | 2 | Open |  | FS
| Develop Custom Reporting Dashboard | Product team will develop stats and report based on the ALM | Project Team/Product Team | 2024-08-11 | 2024-08-13 | 2 | Open |  | FS
| Review Listen Mode - Internal | review the data captured in PLM | Project Team/Product Team | 2024-08-14 | 2024-08-16 | 2 | Open |  | FS
| Review Listen Mode - External ( client) | Showcase data of PLM with client | Project Team/Client | 2024-08-14 | 2024-08-16 | 2 | Open |  | FS
| Go-No Go (pahse Closure) | ask client for the phase closure | Client/ Project Team | 2024-08-17 | 2024-08-19 | 2 | Open |  | FS
Formulas:
End = [Start]+[Duration]
Start = [End, row above]+1

## Data
<select>
Open
In-Progress
Closed