## Leslie
Task(s) & Milestones | Desctiption | Assignee | Start Date | End Date | Duration | Status | Comment
1. Intro Call (1 Week)
a. Intro call with Wave iX team (internal call) | i.e. all participants partner, PMO, Pavel & Eric. | Wave iX Team |  |  |  | Done | need to make sure we must have absolute dates and status
b. Intro call with client - Kick off and POC identification | i.e. what value we are delivering with the proposed solution. | Wave iX Team,Client |  |  |  | In-Progress
2. Discovery Workshop (1 Week)
a. Identify Stakeholders | i.e. Roles and Responsibilities from Client and Wave iX end. | Wave iX Team | 2025-01-06 | 2025-01-13 | 7 | In-Progress
b. Gather Operational Requirements and usecase identification for automation | i.e. Document client’s IVR, FAQs, operational workflows and gather other supporting materials and documentation from Client services or Operations | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 | 7 | In-Progress
c. Identify Key Operational Pain Points | i.e. Highlight areas for improvement | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 | 7 | In-Progress
d. Identify and Establish KPI(s) and their current and forecasted value. | Meet up with the CS and Operations and gather list of KPIs measuring the success criteria | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 | 7 | In-Progress
e. Compliance/Security Review (if required) | Ensure solution design meets data privacy, security, and compliance standards. | Wave iX Team, Security | 2025-01-06 | 2025-01-13 | 7 | Done
3. Tech Discovery (1 Week)
a. Tech sessions for understanding client platform (if required) | e.g. CCaas? CRM? KB? - This information may be available during sales process. | Wave iX Team/Client | 2025-01-13 | 2025-01-24 | 11 | Done
b. Assessment of the platform and see if we need to develop customizations for the enablement. | Wave iX team will check if we have out of the box integration solution or do we need to develop customize code | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | Done
c. Collect URLs VoIP/Https from both end to whitelist | For establishing the Secure communication whitelisting from both ends needs to be done. Genesys & wave IX , Wave IX and CRM | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | In-Progress
h. Tech session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client. | Conduct a session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client and discuss the API details | Wave iX Team/Client | 2025-01-13 | 2025-01-24 | 11 | Done
g. Get API Access from source CCaaS, CRM, KB i.e. User Creation | Access provision from the on the CCaaS, CRM, KBs. | Client | 2025-01-13 | 2025-01-24 | 11 | In-Progress
f. Review API Documentation and prepare questions | documentation of CRMs, ACDs etc | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | In-Progress
e. System Architectural Diagram | i.e. diagram to visually analyze the configuration scenario | Wave iX Team/Ops | 2025-01-13 | 2025-01-24 | 11 | Done
d. Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | Done
e. Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Wave iX Team | 2025-01-13 | 2025-01-24 | 11 | Done
4. Listen Mode Enablement(3weeks) (if required)
a. Assess Telephony Requirements | i.e. DID creation, Call Forwarding | Wave iX Team |  |  |  | Done
b. Plan Telephony Integration | i.e. raise formal tickets or request | Wave iX Team |  |  |  | Done
c. Implement Telephony Integration | Implement Telephony Integration | Wave iX Team |  |  |  | In-Progress
d. Integration Testing | i.e. make Test Calls E2E and monitor logs, take Go-No Go | Wave iX Team |  |  |  | To-Do
e. Enablement of Listening Mode | Enablement of Listening Mode | Wave iX Team
5. Listen Mode Data Analysis
Collect Data and build Analytics |  | BI |  |  |  | To-Do
Use case identification, |  | BI |  |  |  | To-Do
Draw Flows, understanding Flows |  | BI |  |  |  | To-Do
5. Scoping(1 Week)
a. Tech sessions with Client POC on Analytics on Listen Mode. | showcase them possession of the calls traffic | Wave iX Team/Client |  |  |  | Done
c. Scoping Call with Client i.e. What needs to be delivered in Subsequent Phases | i.e. Phase 1 Flow 1, Flow2, Flow 3 .Phase 2 Flow 4, Flow 5, Flow 6. | Wave iX Team/Client | 2025-01-13 | 2025-01-17 | 4 | Done
d. Identify Call routing Flows and detailed Usecase steps from Operations | need detailed step by step of each flow right from the call receiving and involving steps in the CRM | Wave iX Team/Operations | 2025-01-13 | 2025-01-17 | 4 | Done
d. Identify FAQs | need to collect and en-scope FAQ(s) that needs to be automated by IVR Bot. It can be available on pubic forum or Operations can guide us |  | 2025-01-27 | 2025-01-31 | 4 | To-do
d. Initiate Tech Session with Client on Mapping Usecases with APIs | Initiate Tech Session with Client on Mapping Usecases with APIs | Wave iX Team/Operations | 2025-01-27 | 2025-01-31 | 4 | To-do
e. Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Wave iX Team/Client | 2025-01-27 | 2025-01-31 | 4 | To-do
f. Develop Formal Scoping Document and Signoff | Formal Scoping Document and Signoff | Wave iX Team/Client | 2025-01-27 | 2025-01-31 |  | Done
6. Integration in Telephony i.e. SIP or PSTN (2 Weeks) |  | Wave iX Team | 2025-01-27 | 2025-01-31
a. Assess Telephony Requirements |  | Wave iX Team | 2025-01-27 | 2025-01-31 |  | Done
b. Plan Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 |  | Done
c. Implement Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 | 4 | To-Do
D. Test Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 | 4 | To-Do
7. BOT Designing |  | Wave iX Team |  |  |  | To-Do
7.1 Setup BOT Persona |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Define Role | helps you define the purpose and context of the AI Agent. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define Tone | tab enables you to define the communication style of the AI Agent | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
c. Instruct BOT | tab provides specific operational guidelines that the AI Agent should follow during its interactions | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.2 Setup Phone | Set up everything required to create a great experience for customers interacting with your AI Agent over the phone | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Define Voice & Language |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define Ambient Sound |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
c. Define End of Speech Recognition Sound |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
d. Define AI Agent is Thinking Sounds |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
e. Define Fine Tunings |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.3 Setup Routing Skill(s) |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Identify client specific routing Skills (destinations) in the IVR i.e. Sales Representative, Activation Options | Need to add client specific routing Skills (destinations) in the IVR i.e. Sales Representative, Activation Options. It depend on the scope and elaborated use cases flows. We need to Add routing skills separately | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define Routing Skill(s) | define the Routing Skill i.e. instructing BOT when to use that particular route, also explicitly mention the parameters which facilitate BOT to deliver to the destination i.e. call summary, customer name, call id, caller number etc | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
1. Define Route i.e. SIP URI with routing Endpoint |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
1. Define instruction to BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
3. Fall back Messages |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
3. Deine Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.4 Setup Knowledge Skill |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Define and Emphasize Source-Only Retrieval |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Filter Questions to Resolve Ambiguities |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
c. Agent Role and Company Context |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
d. Consistent Prompt Framework |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
e. Source Formatting |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
f. Logical Grouping of Sources in Collections |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
g. Content Length |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
h. Adapt Content for Telephony |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7.5 Setup Custom Skill(s) | The Custom Skill enables AI agents to interact with third-party systems using APIs. This allows AI agents to retrieve and send data to external systems, perform actions such as updating records or initiating transactions, and provide users with a seamless experience by integrating various backend systems into a single conversational interface | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
a. Identify client specific Custom Skills (destinations) where BOT needs to interact with the API | Identify client specific Custom Skills (destinations) where BOT needs to interact with the API for example WISMO, Specfic Details about plan. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
b. Define client specific Custom Skills (destinations) | Instruct AI BOT explicitly on WYSIWYG basis. Instruct when to use this skill. Define API End Point whenever this skill triggers. | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
1. Instruct BOT |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
2. Configuring API Call |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
3. Adding Parameters |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | our dev team will be able to do this
7. 6 Simulations & Prompt Engineering |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do
a. Define LLM Params |  | Wave iX Team | 2025-02-03 | 2025-02-11 |  | To-Do
c. CX Design: Set up simulations and evaluations |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | Keep it for now, will see it later
d. CX Design: AMP Prompt Engineering |  | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do | Keep it for now, will see it later
8. Integration Backend System (2 Weeks) | i.e. Wave iX services Integration with CCaaS's and CRM's APIs. |  | 2025-02-03 | 2025-02-11 |  | To-Do
a. Implementation of Use Cases in Wave iX and Integration Feedback | Implementation of Use Cases in Wave iX and Integration Feedback | Wave iX Team | 2025-02-03 | 2025-02-11 | 8 | To-Do
9. QA & QC |  | Wave iX Team |  |  |  | To-Do
a. Develop Test case for Testing AI BOT |  | Wave iX Team | 2025-02-12 | 2025-02-19 |  | To-Do
a. BOT Testing |  | Wave iX Team | 2025-02-12 | 2025-02-19 |  | To-Do
c. Define Centralized Space for Reporitng and sharing Bugs |  | Wave iX Team | 2025-02-12 | 2025-02-19 | 7 | To-Do
d. Bug Fixing & Regression Testing |  | Wave iX Team | 2025-02-12 | 2025-02-19 |  | To-Do
e. Go-No Go. Sign Off | Go-No Go. Sign Off | Wave iX Team | 2025-02-12 | 2025-02-19 | 7 | To-Do
9. User Acceptance Testing & Optimization |  | Wave iX Team |  |  |  | To-Do
a. Identification of Test Case with the help of CS & Ops. | Ops will come up with the pre-defined test cases | Ops | 2025-01-20 | 2025-01-24 | 4 | To-Do
b. Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Wave iX Team | 2025-02-17 | 2025-02-21 | 4 | To-Do
b. Schedule and Conduct Session for testing on Official Bridges. | Schedule and Conduct Session for testing on Official Bridges. | Wave iX Team | 2025-02-17 | 2025-02-19 | 2 | To-Do
c. Review Results with Wave iX Team | Review Results with Wave iX Team and see if we need to develop | Wave iX Team | 2025-01-20 | 2025-01-20 | 0 | To-Do
Go-No Go Sign Off from Project Team |  |  | 2025-01-20 | 2025-01-20 | 0 | To-Do
10. Go-Live | [5 empty] | To-Do
a. Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
b. Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
c. Bridge Reservation and Go-Live | Bridge Reservation and Go-Live | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
d. Go-Live |  | Wave iX Team | 2025-02-24 | 2025-02-24 |  | To-Do
e. Monitoring bridge | Monitoring bridge | Wave iX Team | 2025-02-24 | 2025-02-28 |  | To-Do
11. Ongoing Testing and Review of Conversations in AMP | [5 empty] | To-Do
a. Adaptation | retrospective | Wave iX Team | 2025-03-03 | 2025-03-05 |  | To-Do
b. Refinements | Refinements | Wave iX Team | 2025-03-06 | 2025-03-07 |  | To-Do