## TiVO
Task(s) & Milestones | Desctiption | Assignee | Start Date | End Date | Duration | Status | Comment
1. Intro Call (1 Week)
a. Intro call with Wave iX team (internal call) | i.e. all participants partner, PMO, Pavel & Eric. | Wave iX Team |  |  |  | Done
b. Intro call with client - Kick off and POC identification | i.e. what value we are delivering with the proposed solution. | Wave iX Team,Client |  |  |  | Done
2. Discovery Workshop (1 Week)
a. Identify Stakeholders | i.e. Roles and Responsibilities from Client and Wave iX end. | Wave iX Team | 2025-01-06 | 2025-01-13 |  | In-Progress | need to ask the roles and POC from Wave iX and generate the
b. Gather Operational Requirements | i.e. Document client’s IVR, FAQs, operational workflows and gather other supporting materials and documentation from Client services or Operations | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 |  | Done
c. Identify Key Operational Pain Points | i.e. Highlight areas for improvement | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 |  | Done
d. Identify and Establish KPI(s) and their current and forecasted value. | Meet up with the CS and Operations and gather list of KPIs measuring the success criteria | Wave iX Team, CS, Ops | 2025-01-06 | 2025-01-13 |  |  | need to be checked with Pavel
e. Compliance/Security Review (if required) | Ensure solution design meets data privacy, security, and compliance standards. | Wave iX Team, Security | 2025-01-06 | 2025-01-13 |  | Done
3. Tech Discovery (1 Week)
a. Tech sessions for understanding client platform (if required) | e.g. CCaas? CRM? KB? - This information may be available during sales process. | Wave iX Team/Client | 2025-01-13 | 2025-01-24 |  | Done
b. Assessment of the platform and see if we need to develop customizations for the enablement. | Wave iX team will check if we have out of the box integration solution or do we need to develop customize code | Wave iX Team | 2025-01-13 | 2025-01-24 |  | Done
c. Collect URLs VoIP/Https from both end to whitelist | For establishing the Secure communication whitelisting from both ends needs to be done. Genesys & wave IX , Wave IX and CRM | Wave iX Team | 2025-01-13 | 2025-01-24 |  | In-Progress | we have access to the dev or staging salesforce. We need to get for the production as well
h. Tech session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client. | Conduct a session with Platforms owners(CCaas, CRM, KB) Owner i.e. Client and discuss the API details | Wave iX Team/Client | 2025-01-13 | 2025-01-24 |  | Done
g. Get API Access from source CCaaS, CRM, KB i.e. User Creation | Access provision from the on the CCaaS, CRM, KBs. | Client | 2025-01-13 | 2025-01-24 |  | In-Progress | we have access to the dev or staging salesforce. We need to get for the production as well
f. Review API Documentation and prepare questions | documentation of CRMs, ACDs etc | Wave iX Team | 2025-01-13 | 2025-01-24 |  | Done
e. System Architectural Diagram | i.e. diagram to visually analyze the configuration scenario | Wave iX Team/Ops | 2025-01-13 | 2025-01-24 |  | Done
d. Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CCaaS and Wave iX | Wave iX Team | 2025-01-13 | 2025-01-24 |  | In-Progress | Need to be discussed with the PMO team internally
e. Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Request Whitelisting of the Wave iX AI Agent URLS for CRM and Wave iX | Wave iX Team | 2025-01-13 | 2025-01-24 |  | In-Progress | Need to be discussed with the PMO team internally
4. Listen Mode Enablement(3weeks) (if required)
a. Assess Telephony Requirements | i.e. DID creation, Call Forwarding | Wave iX Team |  |  |  | Done
b. Plan Telephony Integration | i.e. raise formal tickets or request | Wave iX Team |  |  |  | Done
c. Implement Telephony Integration | Implement Telephony Integration | Wave iX Team |  |  |  | In-Progress
d. Integration Testing | i.e. make Test Calls E2E and monitor logs, take Go-No Go | Wave iX Team |  |  |  | To-Do
e. Enablement of Listening Mode | Enablement of Listening Mode | Wave iX Team |  |  |  |  | Not required
5. Listen Mode Data Analysis
Collect Data and build Analytics |  | BI |  |  |  | To-Do
Use case identification, |  | BI |  |  |  | To-Do
Draw Flows, understanding Flows |  | BI |  |  |  | To-Do
5. Scoping(1 Week)
a. Tech sessions with Client POC on Analytics on Listen Mode. | showcase them possession of the calls traffic | Wave iX Team/Client |  |  |  | Done
b. Use Case identification that needs to be automated. | Propose set of usecase to client that can be automated and get beneficial. | Wave iX Team/Client | 2025-01-06 | 2025-01-10 |  | Done
c. Scoping Call with Client i.e. What needs to be delivered in Subsequent Phases | i.e. Phase 1 Flow 1, Flow2, Flow 3 .Phase 2 Flow 4, Flow 5, Flow 6. | Wave iX Team/Client | 2025-01-13 | 2025-01-17 |  | Done
d. Identify Call routing Flows and detailed Usecase steps from Operations | need detailed step by step of each flow right from the call receiving and involving steps in the CRM | Wave iX Team/Operations | 2025-01-13 | 2025-01-17 |  | Done
d. Identify FAQs | need to collect and en-scope FAQ(s) that needs to be automated by IVR Bot. It can be available on pubic forum or Operations can guide us |  | 2025-01-27 | 2025-01-31 |  | To-do | TiVo's FAQ are available on the public forum, we can advise Development team to pull the data from the public forums via Web Scrapping
d. Initiate Tech Session with Client on Mapping Usecases with APIs | Initiate Tech Session with Client on Mapping Usecases with APIs | Wave iX Team/Operations | 2025-01-27 | 2025-01-31 |  | To-do
e. Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Identify Use cases and API Endpoints i.e. tech sessions between the Clients and Wave iX team | Wave iX Team/Client | 2025-01-27 | 2025-01-31 |  | To-do
f. Develop Formal Scoping Document and Signoff | Formal Scoping Document and Signoff | Wave iX Team/Client |  |  |  | Done
6. Integration in Telephony i.e. SIP or PSTN (2 Weeks)
a. Assess Telephony Requirements |  | Wave iX Team |  |  |  | Done | need to check if we can remove the earlier block for our TiVo client since we don’t need Listening mode
b. Plan Telephony Integration |  | Wave iX Team |  |  |  | Done
c. Implement Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 |  | To-Do
D. Test Telephony Integration |  | Wave iX Team | 2025-01-27 | 2025-01-31 |  | To-Do
7. Setup Routing Skill |  |  | 2025-01-27 | 2025-01-31 |  | To-Do | our dev team will be able to do this
8. Setup Knowledge Skill |  |  | 2025-02-03 | 2025-02-14
a. Define and Emphasize Source-Only Retrieval |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
b. Filter Questions to Resolve Ambiguities |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
c. Agent Role and Company Context |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
d. Consistent Prompt Framework |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
e. Source Formatting |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
f. Logical Grouping of Sources in Collections |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
g. Content Length |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
h. Adapt Content for Telephony |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
9. Setup Custom Skill |  |  | 2025-02-03 | 2025-02-14 |  | To-Do | our dev team will be able to do this
10. Setup BOT AI Agent |  |  | 2025-02-03 | 2025-02-14
a. AI Agent(bot) Development - by CXD | using Studio, build a BOT AI agent and assign Task | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do
b. CX Design: Integrate knowledge sources |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do
c. CX Design: Set up simulations and evaluations |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do
d. CX Design: AMP Prompt Engineering |  | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do
11. Integration Backend System (2 Weeks) | i.e. Wave iX services Integration with CCaaS's and CRM's APIs.
c. Implementation of Use Cases in Wave iX and Integration Feedback | Implementation of Use Cases in Wave iX and Integration Feedback | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do
d. Product Increment Review & Retro | demo | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do
e. Go-No Go. Sign Off | Go-No Go. Sign Off | Wave iX Team | 2025-02-03 | 2025-02-14 |  | To-Do
12. User Acceptance Testing & Optimization
a. Identification of Test Case with the help of CS & Ops. | Ops will come up with the pre-defined test cases | Ops | 2025-01-20 | 2025-01-24 |  | To-Do
b. Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Build Performance Report for the implementation and Monitor of KPI i.e. NPS | Wave iX Team | 2025-02-17 | 2025-02-21 |  | To-Do
b. Schedule and Conduct Session for testing on Official Bridges. | Schedule and Conduct Session for testing on Official Bridges. | Wave iX Team | 2025-02-17 | 2025-02-19 |  | To-Do
c. Review Results with Wave iX Team | Review Results with Wave iX Team and see if we need to develop | Wave iX Team | 2025-01-20 | 2025-01-20 |  | To-Do
Go-No Go Sign Off from Project Team |  |  | 2025-01-20 | 2025-01-20 |  | To-Do
13. Go-Live
a. Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Develop & Establish Go-Live Plan (what if, Proper Rollback, Maintenance Window) | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
b. Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Formally Notification of Go-Live to all Stakeholders i.e. client, Operations, Client Services | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
c. Bridge Reservation and Go-Live | Bridge Reservation and Go-Live | Wave iX Team | 2025-02-10 | 2025-02-10 |  | To-Do
d. Go-Live |  | Wave iX Team | 2025-02-24 | 2025-02-24
e. Monitoring bridge | Monitoring bridge | Wave iX Team | 2025-02-24 | 2025-02-28 |  | To-Do
14. Ongoing Testing and Review of Conversations in AMP
a. Adaptation | retrospective | Wave iX Team | 2025-03-03 | 2025-03-05 |  | To-Do
b. Refinements | Refinements | Wave iX Team | 2025-03-06 | 2025-03-07 |  | To-Do